## Start here
Free estimating spreadsheet from Bidfident
Conduit runs: estimate
Canada version, blank copy
Version 0.1, October 2026. The latest copy is at bidfident.com.
What this is
A ready-to-use estimating spreadsheet for conduit runs. Price your work line by line, compare subtrade quotes, add your running costs and profit, and get a bid total that adds up to the cent. Every figure is worked out by a formula, so change a rate or a quantity and everything follows.
This copy | This is the blank copy. The trades and equipment on the Rates tab are suggestions: rename them and type your own rates. The worked-example copy shows the same layout filled in with a made-up job.
How to use it, in five steps
1 Rates | Type your hourly rates for each trade and each piece of equipment, the job length in weeks, and your percentages (contingency, fee, bonding, insurance, GST).
2 Estimate | One row for each line of work. Type the quantity, the hours each unit takes and what the materials cost. Pick the trade and equipment from the lists, and a cost code from the Codes tab, or type your own. Mark a line Excluded to price it without counting it, for example an option. A line that needs a look turns pink.
3 Subtrades and overhead | On the Subtrades tab, type the quotes you have for each package. The lowest is carried unless you pick another. On the Overhead tab, add running costs; weekly and monthly ones follow the job length.
4 Bid summary | Your bid total, worked out in order: direct cost, contingency, fee, bonding, insurance. Nothing to type here.
5 Quote | A one-page quote to send to your customer. Type your details, the scope and what is not included; the price comes from the Bid summary tab. Print it or save it as a PDF.
Which cells are which
Yellow | You type here.
Grey | Worked out for you. These cells are locked so a formula cannot be typed over by accident.
How the figures are worked out
Labour = hours x hourly rate. Materials = quantity x price x (1 + waste %). Equipment = hours x its rate. Each of those is rounded to the cent, half up, and a line is their sum. Quantities, hours and rates are never rounded, and totals add up the rounded amounts, so every column adds up exactly. Then: direct cost = own work + subtrades + overhead. Contingency is a percentage of the direct cost, fee of direct cost plus contingency. Bonding and insurance are each a percentage of the subtotal before them (not of each other). GST is shown beside the bid total and is not part of it.
Good to know
Locked cells | Only the yellow cells, and the boxes on the Quote, can be typed in. To change a formula, unprotect the sheet. In Excel: Review, then Unprotect Sheet (there is no password). In Google Sheets: Data, then Protect sheets and ranges, then remove the protection.
Room | There is room for 60 lines, 8 packages and 12 running costs. For a bigger job, use a second copy for part of the work.
Check before you send | This is a tool for your own estimating. Check every figure before you send a bid. Free to use for your own bids; please do not resell it.
When your spreadsheet gets heavy
If you end up with lots of bids, changing rates, or more than one person working on them, Bidfident does the same sums on a page, keeps every bid with its saved versions, and totals by cost code and area. You can try it on an example job first. It can read the Estimate tab of this spreadsheet, so your lines come across.
See Bidfident | bidfident.com/ca

## Rates
Free estimating spreadsheet from Bidfident
Rates and job details
Type your rates here once. Every line on the Estimate tab picks them up, so changing a rate here changes the whole bid. Yellow cells are for you.
Job details
Job name |  | Shown on the Bid summary tab.
Location
Bid due
Job length (weeks) |  | Weekly and monthly items on the Overhead tab follow this.
Labour rates
Trade | Rate per hour ($) | Pick the trade by this name in the Trade column on the Estimate tab.
Utility labourer
Equipment operator
Survey technician
Asphalt raker
Standard rate (lines with no trade picked) |  | Used for a line that has hours but no trade, or a trade that is not on this list.
Equipment rates
Equipment | Rate per hour ($) | Pick it by this name in the Equipment column on the Estimate tab.
Mini excavator
Plate compactor
Percentages (type 3 for 3%)
Contingency (%) |  | Added to the direct cost, for what you cannot yet see.
Fee (%) |  | Your profit, added to the direct cost plus contingency.
Bonding (%) |  | Taken from the subtotal. Leave at 0 if you are not bonded.
Insurance (%) |  | Taken from the same subtotal as bonding, not from each other.
GST (%) |  | Shown for reference, apart from the bid total.

## Estimate
Free estimating spreadsheet from Bidfident
Conduit runs: estimate
One row per line of work. Type in the yellow cells; the grey cells are worked out for you. Hours, labour, materials and equipment are each rounded to the cent, so every column adds up exactly. Hold your pointer over a heading for what it means.
You type | [14 empty] | Worked out for you
Cost code | Area | Description | Qty | Unit | Trade | Hrs/unit | Rate override | Mat $/unit | Waste % | Equipment | Location | Equip hrs/unit | Excluded | Notes | Line hours | Hourly rate used | Cost of labour | Cost of materials | Cost of equipment | Line total | Line price per unit | Check this line
[11 empty] | Totals, lines counted |  |  |  | 0 |  | 0 | 0 | 0 | 0
[11 empty] | Total of lines left out (Excluded = Yes) | [8 empty] | 0
Note on B6: Your cost code, for example 09 100. Pick one from the Codes tab, or type your own. Optional.
Note on C6: Groups lines, for example a floor or a phase. Optional.
Note on D6: What the line is. Optional but useful.
Note on E6: How much, in the unit next to it. Use a minus sign for a credit.
Note on F6: For example m2, SF, LF, ea.
Note on G6: Who does the work. Pick from your list on the Rates tab. Leave blank for the standard rate.
Note on H6: Hours of work for one unit.
Note on I6: Only if this one line has its own hourly rate. Leave blank to use the trade's rate. A typed 0 counts as a rate of 0.
Note on J6: Material cost for one unit.
Note on K6: Allowance for waste, for example 5 for 5%.
Note on L6: Pick from your list on the Rates tab. Optional.
Note on M6: A room or zone, for information. Optional.
Note on N6: Only if the equipment runs for a different number of hours than the crew. Leave blank to use the crew's hours. A typed 0 counts as 0.
Note on O6: Pick Yes to price the line but leave it out of every total, for example an option the owner has not decided on.
Note on P6: Anything you want to remember about the line. Not used in any sum.
Note on Q6: Quantity x hours per unit.
Note on R6: The line's own rate if it has one, otherwise the trade's rate, otherwise the standard rate.
Note on S6: Line hours x hourly rate, rounded to the cent.
Note on T6: Quantity x material price x (1 + waste %), rounded to the cent.
Note on U6: Hours x the equipment rate, rounded to the cent. The hours are the crew's unless you typed equipment hours.
Note on V6: Labour + materials + equipment.
Note on W6: Line total divided by the quantity, rounded to the cent. For information only.
Note on X6: A plain note if something on the line needs a look.
Note on V69: What the lines marked Excluded come to. For information only: it is added to nothing.

## Subtrades
Free estimating spreadsheet from Bidfident
Subtrades
One row for each package of work you let to a subtrade. Type up to four quotes. The lowest quote is carried unless you pick another by number. No quotes yet? Type an allowance and it is carried until a quote comes in.
You type | [13 empty] | Worked out for you
Cost code | Package | In the bid? | Quote 1 from | Amount | Quote 2 from | Amount | Quote 3 from | Amount | Quote 4 from | Amount | Use quote no. | Allowance | Notes | Lowest quote | Quote carried | Carried from | Amount | In the bid
[16 empty] | Total in the bid |  | 0
Note on C6: Type a name to start a package, for example Firestopping.
Note on D6: Leave blank or Yes to count the package. No leaves it out of the bid but keeps its figures.
Note on M6: Leave blank to carry the lowest quote. Type 1, 2, 3 or 4 to carry that quote instead.
Note on N6: Carried only when there are no quotes yet.
Note on P6: The lowest quote above zero.
Note on Q6: Which quote is carried (1 to 4). The lowest unless you picked another.
Note on S6: The carried quote, or the allowance when there are no quotes.
Note on T6: What goes into the bid: the amount, or 0 if the package is switched off.

## Overhead
Free estimating spreadsheet from Bidfident
Overhead
Running costs that are not tied to one line of work: supervision, site office, small tools, bins. Weekly and monthly items can follow the job length from the Rates tab, so they grow if the job runs longer.
You type | [5 empty] | Worked out for you
Cost code | Description | Unit | Follows job length? | Quantity | Rate | Quantity used | Amount
[5 empty] | Total |  | 0
Note on D6: wk = per week, mo = per month, day, hr, LS = lump sum, ea = each.
Note on E6: Yes makes a weekly (wk) or monthly (mo) item follow the job length on the Rates tab. Other units ignore it.
Note on F6: How many, when the item does not follow the job length.
Note on H6: The quantity that is used: the job length (in weeks, or in months = weeks divided by 52 over 12) for items that follow it, otherwise what you typed.
Note on I6: Quantity used x rate, rounded to the cent.

## Bid summary
Free estimating spreadsheet from Bidfident
Bid summary
Your bid, worked out in the order the calculations run. Each amount is rounded to the cent where it is worked out, so the column adds up exactly. Nothing on this tab is typed: change the other tabs and it follows.
Job
Location ¦ Bid due ¦ Length
Item | Amount | How it is worked out
Own work | 0 | The lines on the Estimate tab, apart from any marked Excluded.
Labour | 0
Materials | 0
Equipment | 0
Subtrades | 0 | The quote carried for each package, or its allowance.
Overhead | 0 | From the Overhead tab.
Direct cost | 0 | Own work + subtrades + overhead
Contingency | 0 | % of direct cost
Fee | 0 | % of direct cost plus contingency
Subtotal before bonding | 0 | Direct cost + contingency + fee.
Bonding | 0 | % of the subtotal
Insurance | 0 | % of the subtotal
Bid total | 0 | The price you submit, before GST.
GST, for reference | 0 | %, shown separately and not part of the bid total
Bid total including GST | 0 | For reference.
Left out of the bid (Excluded lines) | 0 | Priced so you can see them, added to nothing.
Lines that need a look | 0 | Every line has what it needs.
When your spreadsheet gets heavy
Bidfident does these same sums on a page, and adds what a spreadsheet cannot do:
Every bid in one place, with saved versions you can compare with now and restore.
Totals by cost code and by area, worked out for you.
It can read the Estimate tab of this spreadsheet, so your lines come across.
See it on an example job:
See Bidfident | bidfident.com/ca

## Quote
Quote |  | Your logo here
Date
Valid for (days)
Valid until
Reference
From
Your business
Contact
Address
To
Customer
Address
Job
Job
Location
Expected length
Scope of work
Not included
Price
Price |  | 0
GST is not included
Terms
Acceptance
Signed for the customer
| Name and signature | Date
Signed for your business
| Name and signature | Date
Prepared with a free estimating spreadsheet from Bidfident, bidfident.com
Note on D2: Delete these words and add your logo: Insert, then Pictures. Keep it inside this box so the page still prints on one sheet.
Note on C3: This page goes to your customer, so its boxes are white, not yellow. Type in the boxes down the page; the job and the price come from the other tabs. Print it or save it as a PDF.
Note on C18: From the Rates tab.
Note on C19: From the Rates tab.
Note on C20: From the Rates tab.
Note on D31: The price is worked out on the Bid summary tab and cannot be typed over here.

## Codes
Free estimating spreadsheet from Bidfident
Starter cost codes
Bidfident's own starter list for conduit runs, with the 01 codes for site set-up and running costs: one code for each kind of work you price. Pick one in the Cost code column on the Estimate tab, or type your own. Every code starts with a two-digit number, which is how Bidfident groups an estimate. Change the list to suit your business: rename, delete, or add codes between the numbers.
Codes
Code | Description | Unit
01 100 | Project management and supervision | wk
01 110 | Mobilization and demobilization | ls
01 120 | Site office and storage | wk
01 130 | Temporary power and lighting | wk
01 140 | Temporary heat and ventilation | wk
01 150 | Washrooms and handwashing | wk
01 160 | Fencing and signs | ls
01 170 | Safety plan and training | ls
01 180 | Safety gear and first aid | ls
01 190 | Permits and fees | ls
01 200 | Insurance and bonds | ls
01 210 | Layout and surveying | day
01 220 | Scaffold and access equipment | wk
01 230 | Hoisting and deliveries | day
01 240 | Dumpsters and waste removal | ea
01 250 | Daily cleaning | wk
01 260 | Final cleaning | ls
01 270 | Protection of existing floors and finishes | ls
01 280 | Site vehicles and fuel | ls
01 290 | Small tools and supplies | ls
01 300 | Drawings and submittals | ls
01 310 | Testing and inspections | ls
01 320 | Handover documents and manuals | ls
01 330 | Warranty and call backs | ls
01 340 | Allowances | ls
01 350 | Overtime and premium time | hr
01 360 | Weather protection | ls
01 370 | Meetings and site paperwork | hr
27 700 | Duct laid in open trench | m
27 710 | Multi way duct banks | m
27 720 | Conduit on walls and bridges | m
27 730 | Concrete encased duct | m
27 740 | Handholes and maintenance holes | ea
27 750 | Elbows and sweeps | ea
27 760 | Couplings and end caps | ea
27 770 | Pull rope installed | m
27 780 | Mandrel and proving | m
27 790 | Warning tape and markers | m
27 800 | Trench backfill | m
27 810 | Road cuts and repair | m2
27 820 | Saw cutting surface | m
27 830 | Road crossings | ea
27 840 | Potholing to find services | ea
27 850 | Traffic control and signs | wk
27 860 | Trench boxes and shoring | wk
27 870 | Excavator and crew | day
27 880 | Extra work by the hour | hr
Free to use for your own bids. Change it to suit your business. Please don't resell it or hand it out as your own list.
Bidfident's own starter list, version 1, October 2026. Not affiliated with or endorsed by CSI, CSC or RICS.