## Start here
Free estimating spreadsheet from Bidfident
Grading: estimate
Canada version, with a worked example
Version 0.1, October 2026. The latest copy is at bidfident.com.
What this is
A ready-to-use estimating spreadsheet for grading. Price your work line by line, compare subtrade quotes, add your running costs and profit, and get a bid total that adds up to the cent. Every figure is worked out by a formula, so change a rate or a quantity and everything follows.
This copy | This copy is filled in with a worked example: rough and fine grading for a school sports field, Airdrie, AB. It is a made-up job with realistic figures, so you can see how it all fits. Change any yellow cell and watch the bid change. The blank copy has the same layout, empty.
How to use it, in five steps
1 Rates | Type your hourly rates for each trade and each piece of equipment, the job length in weeks, and your percentages (contingency, fee, bonding, insurance, GST).
2 Estimate | One row for each line of work. Type the quantity, the hours each unit takes and what the materials cost. Pick the trade and equipment from the lists, and a cost code from the Codes tab, or type your own. Mark a line Excluded to price it without counting it, for example an option. A line that needs a look turns pink.
3 Subtrades and overhead | On the Subtrades tab, type the quotes you have for each package. The lowest is carried unless you pick another. On the Overhead tab, add running costs; weekly and monthly ones follow the job length.
4 Bid summary | Your bid total, worked out in order: direct cost, contingency, fee, bonding, insurance. Nothing to type here.
5 Quote | A one-page quote to send to your customer. Type your details, the scope and what is not included; the price comes from the Bid summary tab. Print it or save it as a PDF.
Which cells are which
Yellow | You type here.
Grey | Worked out for you. These cells are locked so a formula cannot be typed over by accident.
How the figures are worked out
Labour = hours x hourly rate. Materials = quantity x price x (1 + waste %). Equipment = hours x its rate. Each of those is rounded to the cent, half up, and a line is their sum. Quantities, hours and rates are never rounded, and totals add up the rounded amounts, so every column adds up exactly. Then: direct cost = own work + subtrades + overhead. Contingency is a percentage of the direct cost, fee of direct cost plus contingency. Bonding and insurance are each a percentage of the subtotal before them (not of each other). GST is shown beside the bid total and is not part of it.
Good to know
Locked cells | Only the yellow cells, and the boxes on the Quote, can be typed in. To change a formula, unprotect the sheet. In Excel: Review, then Unprotect Sheet (there is no password). In Google Sheets: Data, then Protect sheets and ranges, then remove the protection.
Room | There is room for 60 lines, 8 packages and 12 running costs. For a bigger job, use a second copy for part of the work.
Check before you send | This is a tool for your own estimating. Check every figure before you send a bid. Free to use for your own bids; please do not resell it.
When your spreadsheet gets heavy
If you end up with lots of bids, changing rates, or more than one person working on them, Bidfident does the same sums on a page, keeps every bid with its saved versions, and totals by cost code and area. You can try it on an example job first. It can read the Estimate tab of this spreadsheet, so your lines come across.
See Bidfident | bidfident.com/ca

## Rates
Free estimating spreadsheet from Bidfident
Rates and job details
Type your rates here once. Every line on the Estimate tab picks them up, so changing a rate here changes the whole bid. Yellow cells are for you.
Job details
Job name | School sports field, grading (example) | Shown on the Bid summary tab.
Location | Airdrie, AB
Bid due | 2026-12-11
Job length (weeks) | 5 | Weekly and monthly items on the Overhead tab follow this.
Labour rates
Trade | Rate per hour ($) | Pick the trade by this name in the Trade column on the Estimate tab.
Equipment operator | 72
Labourer | 52
Grade checker | 60
Pipelayer | 66
Standard rate (lines with no trade picked) | 80 | Used for a line that has hours but no trade, or a trade that is not on this list.
Equipment rates
Equipment | Rate per hour ($) | Pick it by this name in the Equipment column on the Estimate tab.
Dozer, D6 class | 150
Motor grader | 150
Smooth drum roller, 10 t | 68
Excavator, 20 t | 165
Percentages (type 3 for 3%)
Contingency (%) | 3 | Added to the direct cost, for what you cannot yet see.
Fee (%) | 10 | Your profit, added to the direct cost plus contingency.
Bonding (%) | 1 | Taken from the subtotal. Leave at 0 if you are not bonded.
Insurance (%) | 0.5 | Taken from the same subtotal as bonding, not from each other.
GST (%) | 5 | Shown for reference, apart from the bid total.

## Estimate
Free estimating spreadsheet from Bidfident
Grading: estimate
One row per line of work. Type in the yellow cells; the grey cells are worked out for you. Hours, labour, materials and equipment are each rounded to the cent, so every column adds up exactly. Hold your pointer over a heading for what it means.
You type | [14 empty] | Worked out for you
Cost code | Area | Description | Qty | Unit | Trade | Hrs/unit | Rate override | Mat $/unit | Waste % | Equipment | Location | Equip hrs/unit | Excluded | Notes | Line hours | Hourly rate used | Cost of labour | Cost of materials | Cost of equipment | Line total | Line price per unit | Check this line
31 370 | Main field | Strip and stockpile topsoil | 14500 | m2 | Equipment operator | 0.008 |  | 0 | 0 | Dozer, D6 class | Field | 0.005 |  |  | 116 | 72 | 8352 | 0 | 10875 | 19227 | 1.33
31 320 | Main field | Cut and fill on site | 6200 | m3 | Equipment operator | 0.03 |  | 0 | 0 | Dozer, D6 class | Field | 0.018 |  |  | 186 | 72 | 13392 | 0 | 16740 | 30132 | 4.86
31 310 | Main field | Fine grading to plus or minus 25 mm | 14500 | m2 | Equipment operator | 0.006 |  | 0 | 0 | Motor grader | Field | 0.004 |  |  | 87 | 72 | 6264 | 0 | 8700 | 14964 | 1.03
31 330 | Main field | Subgrade compaction and proof roll | 14500 | m2 | Labourer | 0.004 |  | 0 | 0 | Smooth drum roller, 10 t | Field | 0.003 |  |  | 58 | 52 | 3016 | 0 | 2958 | 5974 | 0.41
31 370 | Main field | Respread topsoil, 150 mm | 14500 | m2 | Equipment operator | 0.007 |  | 0 | 0 | Dozer, D6 class | Field | 0.005 |  |  | 101.5 | 72 | 7308 | 0 | 10875 | 18183 | 1.25
31 370 | Main field | Alternate 1: sand-based rootzone mix, 100 mm, over respread topsoil | 1450 | m3 | Equipment operator | 0.03 |  | 48 | 10 | Dozer, D6 class | Field | 0.02 | Yes |  | 43.5 | 72 | 3132 | 76560 | 4350 | 84042 | 57.96
31 400 | Main field | Seed and fertilize, sports field mix | 14500 | m2 | Labourer | 0.003 |  | 0.42 | 5 |  | Field |  |  |  | 43.5 | 52 | 2262 | 6394.5 | 0 | 8656.5 | 0.6
31 310 | Main field | Hand rake and pick stones, finished field, Saturday crew | 14500 | m2 | Labourer | 0.002 | 78 | 0 | 0 |  | Field |  |  |  | 29 | 78 | 2262 | 0 | 0 | 2262 | 0.16
31 410 | Main field | Grade checks with GPS rover, field | 14500 | m2 | Grade checker | 0.0008 |  | 0 | 0 |  | Field |  |  |  | 11.6 | 60 | 696 | 0 | 0 | 696 | 0.05
31 400 | Main field | Erosion control blanket on slopes | 1600 | m2 | Labourer | 0.02 |  | 2.8 | 10 |  | Perimeter |  |  |  | 32 | 52 | 1664 | 4928 | 0 | 6592 | 4.12
31 370 | Parking area | Strip and stockpile topsoil | 4200 | m2 | Equipment operator | 0.008 |  | 0 | 0 | Dozer, D6 class | East side | 0.005 |  |  | 33.6 | 72 | 2419.2 | 0 | 3150 | 5569.2 | 1.33
31 320 | Parking area | Cut to subgrade, parking area | 3100 | m3 | Equipment operator | 0.03 |  | 0 | 0 | Dozer, D6 class | East side | 0.018 |  |  | 93 | 72 | 6696 | 0 | 8370 | 15066 | 4.86
31 310 | Parking area | Fine grading to plus or minus 25 mm | 4200 | m2 | Equipment operator | 0.006 |  | 0 | 0 | Motor grader | East side | 0.004 |  |  | 25.2 | 72 | 1814.4 | 0 | 2520 | 4334.4 | 1.03
31 330 | Parking area | Subgrade compaction and proof roll | 4200 | m2 | Labourer | 0.004 |  | 0 | 0 | Smooth drum roller, 10 t | East side | 0.003 |  |  | 16.8 | 52 | 873.6 | 0 | 856.8 | 1730.4 | 0.41
31 350 | Parking area | Geotextile separator on subgrade | 4200 | m2 | Labourer | 0.008 |  | 1.8 | 10 |  | East side |  |  |  | 33.6 | 52 | 1747.2 | 8316 | 0 | 10063.2 | 2.4
31 370 | Parking area | Respread topsoil, 150 mm | 900 | m2 | Equipment operator | 0.007 |  | 0 | 0 | Dozer, D6 class | East side | 0.005 |  |  | 6.3 | 72 | 453.6 | 0 | 675 | 1128.6 | 1.25
31 370 | Access road | Strip and stockpile topsoil | 1800 | m2 | Equipment operator | 0.008 |  | 0 | 0 | Dozer, D6 class | West side | 0.005 |  |  | 14.4 | 72 | 1036.8 | 0 | 1350 | 2386.8 | 1.33
31 320 | Access road | Cut and fill, access road | 1400 | m3 | Equipment operator | 0.03 |  | 0 | 0 | Dozer, D6 class | West side | 0.018 |  |  | 42 | 72 | 3024 | 0 | 3780 | 6804 | 4.86
31 310 | Access road | Fine grading to plus or minus 25 mm | 1800 | m2 | Equipment operator | 0.006 |  | 0 | 0 | Motor grader | West side | 0.004 |  |  | 10.8 | 72 | 777.6 | 0 | 1080 | 1857.6 | 1.03
31 330 | Access road | Subgrade compaction and proof roll | 1800 | m2 | Labourer | 0.004 |  | 0 | 0 | Smooth drum roller, 10 t | West side | 0.003 |  |  | 7.2 | 52 | 374.4 | 0 | 367.2 | 741.6 | 0.41
31 380 | Access road | Shape roadside ditches | 260 | m | Equipment operator | 0.08 |  | 0 | 0 | Motor grader | Perimeter | 0.05 |  |  | 20.8 | 72 | 1497.6 | 0 | 1950 | 3447.6 | 13.26
31 380 | Access road | Culvert, 450 mm CSP, with end treatment | 24 | m | Pipelayer | 0.6 |  | 145 | 0 | Excavator, 20 t | West side | 0.4 |  |  | 14.4 | 66 | 950.4 | 3480 | 1584 | 6014.4 | 250.6
31 370 | Access road | Respread topsoil, 150 mm | 600 | m2 | Equipment operator | 0.007 |  | 0 | 0 | Dozer, D6 class | West side | 0.005 |  |  | 4.2 | 72 | 302.4 | 0 | 450 | 752.4 | 1.25
31 380 | Subdrainage | Subdrain trench excavation, 600 mm deep | 1200 | m | Equipment operator | 0.03 |  | 0 | 0 | Excavator, 20 t | Field | 0.02 |  |  | 36 | 72 | 2592 | 0 | 3960 | 6552 | 5.46
31 380 | Subdrainage | Perforated subdrain, 100 mm, laid in trench | 1200 | m | Pipelayer | 0.06 |  | 5.6 | 5 |  | Field |  |  |  | 72 | 66 | 4752 | 7056 | 0 | 11808 | 9.84
31 340 | Subdrainage | Drain stone, 20 mm clear | 160 | m3 | Labourer | 0.3 |  | 52 | 10 |  | Field |  |  |  | 48 | 52 | 2496 | 9152 | 0 | 11648 | 72.8
31 380 | Subdrainage | Header drain, 200 mm perforated | 240 | m | Pipelayer | 0.12 |  | 22 | 5 | Excavator, 20 t | Perimeter | 0.05 |  |  | 28.8 | 66 | 1900.8 | 5544 | 1980 | 9424.8 | 39.27
31 380 | Subdrainage | Catch basin, 600 mm precast, with outlet | 3 | ea | Pipelayer | 6 |  | 1450 | 0 | Excavator, 20 t | Perimeter | 2 |  |  | 18 | 66 | 1188 | 4350 | 990 | 6528 | 2176
[11 empty] | Totals, lines counted |  |  |  | 1189.7 |  | 80112 | 49220.5 | 83211 | 212543.5
[11 empty] | Total of lines left out (Excluded = Yes) | [8 empty] | 84042
Note on B6: Your cost code, for example 09 100. Pick one from the Codes tab, or type your own. Optional.
Note on C6: Groups lines, for example a floor or a phase. Optional.
Note on D6: What the line is. Optional but useful.
Note on E6: How much, in the unit next to it. Use a minus sign for a credit.
Note on F6: For example m2, SF, LF, ea.
Note on G6: Who does the work. Pick from your list on the Rates tab. Leave blank for the standard rate.
Note on H6: Hours of work for one unit.
Note on I6: Only if this one line has its own hourly rate. Leave blank to use the trade's rate. A typed 0 counts as a rate of 0.
Note on J6: Material cost for one unit.
Note on K6: Allowance for waste, for example 5 for 5%.
Note on L6: Pick from your list on the Rates tab. Optional.
Note on M6: A room or zone, for information. Optional.
Note on N6: Only if the equipment runs for a different number of hours than the crew. Leave blank to use the crew's hours. A typed 0 counts as 0.
Note on O6: Pick Yes to price the line but leave it out of every total, for example an option the owner has not decided on.
Note on P6: Anything you want to remember about the line. Not used in any sum.
Note on Q6: Quantity x hours per unit.
Note on R6: The line's own rate if it has one, otherwise the trade's rate, otherwise the standard rate.
Note on S6: Line hours x hourly rate, rounded to the cent.
Note on T6: Quantity x material price x (1 + waste %), rounded to the cent.
Note on U6: Hours x the equipment rate, rounded to the cent. The hours are the crew's unless you typed equipment hours.
Note on V6: Labour + materials + equipment.
Note on W6: Line total divided by the quantity, rounded to the cent. For information only.
Note on X6: A plain note if something on the line needs a look.
Note on V69: What the lines marked Excluded come to. For information only: it is added to nothing.

## Subtrades
Free estimating spreadsheet from Bidfident
Subtrades
One row for each package of work you let to a subtrade. Type up to four quotes. The lowest quote is carried unless you pick another by number. No quotes yet? Type an allowance and it is carried until a quote comes in.
You type | [13 empty] | Worked out for you
Cost code | Package | In the bid? | Quote 1 from | Amount | Quote 2 from | Amount | Quote 3 from | Amount | Quote 4 from | Amount | Use quote no. | Allowance | Notes | Lowest quote | Quote carried | Carried from | Amount | In the bid
31 410 | Surveying and grade checks | Yes | Bidder A | 8900 | Bidder B | 7600 | Bidder C | [5 empty] | Bidder C: Declined | 7600 | 2 | Bidder B | 7600 | 7600
31 360 | Compaction testing | Yes | Bidder A | 6200 | Bidder B | 5800 | [6 empty] | Bidder A: Incl. proctors | 5800 | 2 | Bidder B | 5800 | 5800
31 370 | Imported topsoil if the site stock runs short, allowance | Yes | [9 empty] | 12000 |  |  |  | Allowance | 12000 | 12000
[16 empty] | Total in the bid |  | 25400
Note on C6: Type a name to start a package, for example Firestopping.
Note on D6: Leave blank or Yes to count the package. No leaves it out of the bid but keeps its figures.
Note on M6: Leave blank to carry the lowest quote. Type 1, 2, 3 or 4 to carry that quote instead.
Note on N6: Carried only when there are no quotes yet.
Note on P6: The lowest quote above zero.
Note on Q6: Which quote is carried (1 to 4). The lowest unless you picked another.
Note on S6: The carried quote, or the allowance when there are no quotes.
Note on T6: What goes into the bid: the amount, or 0 if the package is switched off.

## Overhead
Free estimating spreadsheet from Bidfident
Overhead
Running costs that are not tied to one line of work: supervision, site office, small tools, bins. Weekly and monthly items can follow the job length from the Rates tab, so they grow if the job runs longer.
You type | [5 empty] | Worked out for you
Cost code | Description | Unit | Follows job length? | Quantity | Rate | Quantity used | Amount
01 100 | Site superintendent | wk | Yes |  | 2900 | 5 | 14500
31 400 | Silt fence and erosion control | LS |  | 1 | 4800 | 1 | 4800
01 110 | Mobilize and demobilize equipment | LS |  | 1 | 7200 | 1 | 7200
01 120 | Site trailer and portable toilet | wk | Yes |  | 305 | 5 | 1525
31 440 | Water truck, dust control | day |  | 10 | 780 | 10 | 7800
[5 empty] | Total |  | 35825
Note on D6: wk = per week, mo = per month, day, hr, LS = lump sum, ea = each.
Note on E6: Yes makes a weekly (wk) or monthly (mo) item follow the job length on the Rates tab. Other units ignore it.
Note on F6: How many, when the item does not follow the job length.
Note on H6: The quantity that is used: the job length (in weeks, or in months = weeks divided by 52 over 12) for items that follow it, otherwise what you typed.
Note on I6: Quantity used x rate, rounded to the cent.

## Bid summary
Free estimating spreadsheet from Bidfident
Bid summary
Your bid, worked out in the order the calculations run. Each amount is rounded to the cent where it is worked out, so the column adds up exactly. Nothing on this tab is typed: change the other tabs and it follows.
Job | School sports field, grading (example)
Location ¦ Bid due ¦ Length | Airdrie, AB ¦ 2026-12-11 ¦ 5 weeks
Item | Amount | How it is worked out
Own work | 212543.5 | The lines on the Estimate tab, apart from any marked Excluded.
Labour | 80112
Materials | 49220.5
Equipment | 83211
Subtrades | 25400 | The quote carried for each package, or its allowance.
Overhead | 35825 | From the Overhead tab.
Direct cost | 273768.5 | Own work + subtrades + overhead
Contingency | 8213.06 | 3% of direct cost
Fee | 28198.16 | 10% of direct cost plus contingency
Subtotal before bonding | 310179.72 | Direct cost + contingency + fee.
Bonding | 3101.8 | 1% of the subtotal
Insurance | 1550.9 | 0.5% of the subtotal
Bid total | 314832.42 | The price you submit, before GST.
GST, for reference | 15741.62 | 5%, shown separately and not part of the bid total
Bid total including GST | 330574.04 | For reference.
Left out of the bid (Excluded lines) | 84042 | Priced so you can see them, added to nothing.
Lines that need a look | 0 | Every line has what it needs.
When your spreadsheet gets heavy
Bidfident does these same sums on a page, and adds what a spreadsheet cannot do:
Every bid in one place, with saved versions you can compare with now and restore.
Totals by cost code and by area, worked out for you.
It can read the Estimate tab of this spreadsheet, so your lines come across.
See it on an example job:
See Bidfident | bidfident.com/ca

## Quote
Quote
Date | 2026-12-11
Valid for (days) | 30
Valid until | 2027-01-10
Reference | Q-0001
From
Your business | Sample Grading Co.
Contact | Name, phone and email
Address | Street, town, postcode
To
Customer | Sample Customer
Address | Street, town, postcode
Job
Job | School sports field, grading (example)
Location | Airdrie, AB
Expected length | 5 weeks
Scope of work
The grading work listed in our estimate, including materials, labour and equipment. Work areas left clean and tidy at the end of each day.
Not included
Anything not listed above. Work by other trades, permits and fees, unless stated above.
Price
Price |  | 314832.42
GST at 5% |  | 15741.62
Total including GST |  | 330574.04
Terms
Payment: 30% on acceptance, the balance within 14 days of completion. This price holds until the date above. Changes to the scope are priced before the work starts.
Acceptance
Signed for the customer
| Name and signature | Date
Signed for Sample Grading Co.
| Name and signature | Date
Prepared with a free estimating spreadsheet from Bidfident, bidfident.com
Note on C3: This page goes to your customer, so its boxes are white, not yellow. Type in the boxes down the page; the job and the price come from the other tabs. Print it or save it as a PDF.
Note on C18: From the Rates tab.
Note on C19: From the Rates tab.
Note on C20: From the Rates tab.
Note on D31: The price is worked out on the Bid summary tab and cannot be typed over here.

## Codes
Free estimating spreadsheet from Bidfident
Starter cost codes
Bidfident's own starter list for grading, with the 01 codes for site set-up and running costs: one code for each kind of work you price. Pick one in the Cost code column on the Estimate tab, or type your own. Every code starts with a two-digit number, which is how Bidfident groups an estimate. Change the list to suit your business: rename, delete, or add codes between the numbers.
Codes
Code | Description | Unit
01 100 | Project management and supervision | wk
01 110 | Mobilization and demobilization | ls
01 120 | Site office and storage | wk
01 130 | Temporary power and lighting | wk
01 140 | Temporary heat and ventilation | wk
01 150 | Washrooms and handwashing | wk
01 160 | Fencing and signs | ls
01 170 | Safety plan and training | ls
01 180 | Safety gear and first aid | ls
01 190 | Permits and fees | ls
01 200 | Insurance and bonds | ls
01 210 | Layout and surveying | day
01 220 | Scaffold and access equipment | wk
01 230 | Hoisting and deliveries | day
01 240 | Dumpsters and waste removal | ea
01 250 | Daily cleaning | wk
01 260 | Final cleaning | ls
01 270 | Protection of existing floors and finishes | ls
01 280 | Site vehicles and fuel | ls
01 290 | Small tools and supplies | ls
01 300 | Drawings and submittals | ls
01 310 | Testing and inspections | ls
01 320 | Handover documents and manuals | ls
01 330 | Warranty and call backs | ls
01 340 | Allowances | ls
01 350 | Overtime and premium time | hr
01 360 | Weather protection | ls
01 370 | Meetings and site paperwork | hr
31 300 | Rough grading | m2
31 310 | Fine grading to final levels | m2
31 320 | Cut and fill earthmoving | m3
31 330 | Subgrade preparation | m2
31 340 | Gravel base placement | m3
31 350 | Geotextile fabric | m2
31 360 | Compaction testing | ea
31 370 | Topsoil spreading | m3
31 380 | Ditches and swales | m
31 390 | Slope shaping and trimming | m2
31 400 | Seed and erosion blanket | m2
31 410 | Grade control and survey | day
31 420 | Dozer or grader with operator | day
31 430 | Compactor roller with operator | day
31 440 | Water truck for dust control | wk
31 450 | Stockpile management | ls
31 460 | Extra work by the hour | hr
Free to use for your own bids. Change it to suit your business. Please don't resell it or hand it out as your own list.
Bidfident's own starter list, version 1, October 2026. Not affiliated with or endorsed by CSI, CSC or RICS.