## Start here
Free estimating spreadsheet from Bidfident
Fibre cabling: estimate
United Kingdom version, with a worked example
Version 0.1, October 2026. The latest copy is at bidfident.com.
What this is
A ready-to-use estimating spreadsheet for fibre cabling. Price your work line by line, compare subcontractor quotes, add your running costs and profit, and get a tender total that adds up to the penny. Every figure is worked out by a formula, so change a rate or a quantity and everything follows.
This copy | This copy is filled in with a worked example: fibre to a rural business park, Near Malton, North Yorkshire. It is a made-up job with realistic figures, so you can see how it all fits. Change any yellow cell and watch the tender change. The blank copy has the same layout, empty.
How to use it, in five steps
1 Rates | Type your hourly rates for each trade and each piece of plant, the job length in weeks, and your percentages (contingency, overheads and profit, bond, insurance, VAT).
2 Estimate | One row for each line of work. Type the quantity, the hours each unit takes and what the materials cost. Pick the trade and plant from the lists, and a cost code from the Codes tab, or type your own. Mark a line Excluded to price it without counting it, for example an option. A line that needs a look turns pink.
3 Subcontractors and preliminaries | On the Subcontractors tab, type the quotes you have for each package. The lowest is carried unless you pick another. On the Preliminaries tab, add running costs; weekly and monthly ones follow the job length.
4 Tender summary | Your tender total, worked out in order: direct cost, contingency, overheads and profit, bond, insurance. Nothing to type here.
5 Quotation | A one-page quotation to send to your customer. Type your details, the scope and what is not included; the price comes from the Tender summary tab. Print it or save it as a PDF.
Which cells are which
Yellow | You type here.
Grey | Worked out for you. These cells are locked so a formula cannot be typed over by accident.
How the figures are worked out
Labour = hours x hourly rate. Materials = quantity x price x (1 + waste %). Plant = hours x its rate. Each of those is rounded to the penny, half up, and a line is their sum. Quantities, hours and rates are never rounded, and totals add up the rounded amounts, so every column adds up exactly. Then: direct cost = own work + subcontractors + preliminaries. Contingency is a percentage of the direct cost, overheads and profit of direct cost plus contingency. Bond and insurance are each a percentage of the subtotal before them (not of each other). VAT is shown beside the tender total and is not part of it.
Good to know
Locked cells | Only the yellow cells, and the boxes on the Quotation, can be typed in. To change a formula, unprotect the sheet. In Excel: Review, then Unprotect Sheet (there is no password). In Google Sheets: Data, then Protect sheets and ranges, then remove the protection.
Room | There is room for 60 lines, 8 packages and 12 running costs. For a bigger job, use a second copy for part of the work.
Check before you send | This is a tool for your own estimating. Check every figure before you send a tender. Free to use for your own tenders; please do not resell it.
When your spreadsheet gets heavy
If you end up with lots of tenders, changing rates, or more than one person working on them, Bidfident does the same sums on a page, keeps every tender with its saved versions, and totals by cost code and area. You can try it on an example job first. It can read the Estimate tab of this spreadsheet, so your lines come across.
See Bidfident | bidfident.com/uk

## Rates
Free estimating spreadsheet from Bidfident
Rates and job details
Type your rates here once. Every line on the Estimate tab picks them up, so changing a rate here changes the whole tender. Yellow cells are for you.
Job details
Job name | Business park fibre (example) | Shown on the Tender summary tab.
Location | Near Malton, North Yorkshire
Tender due | 2026-11-20
Job length (weeks) | 5 | Weekly and monthly items on the Preliminaries tab follow this.
Labour rates
Trade | Rate per hour (£) | Pick the trade by this name in the Trade column on the Estimate tab.
Fibre technician | 27
Overhead linesman | 30
Labourer | 22
Fibre jointer | 30
Standard rate (lines with no trade picked) | 27 | Used for a line that has hours but no trade, or a trade that is not on this list.
Plant rates
Plant | Rate per hour (£) | Pick it by this name in the Plant column on the Estimate tab.
Cherry picker (MEWP) | 45
Mini digger | 18
Cable winch, trailer-mounted | 20
Percentages (type 3 for 3%)
Contingency (%) | 3 | Added to the direct cost, for what you cannot yet see.
Overheads and profit (%) | 10 | Your profit, added to the direct cost plus contingency.
Bond (%) | 1 | Taken from the subtotal. Leave at 0 if you are not bonded.
Insurance (%) | 0.5 | Taken from the same subtotal as bond, not from each other.
VAT (%) | 20 | Shown for reference, apart from the tender total.

## Estimate
Free estimating spreadsheet from Bidfident
Fibre cabling: estimate
One row per line of work. Type in the yellow cells; the grey cells are worked out for you. Hours, labour, materials and equipment are each rounded to the penny, so every column adds up exactly. Hold your pointer over a heading for what it means.
You type | [14 empty] | Worked out for you
Cost code | Area | Description | Qty | Unit | Trade | Hrs/unit | Rate override | Mat £/unit | Waste % | Plant | Location | Equip hrs/unit | Excluded | Notes | Line hours | Hourly rate used | Cost of labour | Cost of materials | Cost of plant | Line total | Line price per unit | Check this line
27.110 | Underground, Park Way | Fibre cable, 144-fibre, pulled through duct | 6200 | m | Fibre technician | 0.008 |  | 2.2 | 3 |  | Park Way |  |  |  | 49.6 | 27 | 1339.2 | 14049.2 | 0 | 15388.4 | 2.48
27.160 | Underground, Park Way | Footway chambers, set and backfilled | 12 | nr | Labourer | 3 |  | 380 | 0 |  | Park Way |  |  |  | 36 | 22 | 792 | 4560 | 0 | 5352 | 446
27.170 | Underground, Park Way | Slack coils and storage brackets | 18 | nr | Fibre technician | 0.75 |  | 25 | 0 |  | Park Way |  |  |  | 13.5 | 27 | 364.5 | 450 | 0 | 814.5 | 45.25
27.110 | Underground, Park Way | Prove existing duct with mandrel and draw rope | 6200 | m | Labourer | 0.003 |  | 0.08 | 0 |  | Park Way |  |  |  | 18.6 | 22 | 409.2 | 496 | 0 | 905.2 | 0.15
27.110 | Underground, Park Way | Duct repairs at blockages, dig and couple | 4 | nr | Labourer | 6 |  | 99 | 0 | Mini digger | Park Way | 2 |  |  | 24 | 22 | 528 | 396 | 144 | 1068 | 267
27.160 | Underground, Park Way | Carriageway covers at entrance crossings | 3 | nr | Labourer | 1 |  | 231 | 0 |  | Park Way |  |  |  | 3 | 22 | 66 | 693 | 0 | 759 | 253
27.100 | Overhead, Moor Lane pole route | Overhead fibre, on catenary wire | 2400 | m | Overhead linesman | 0.02 |  | 1.8 | 3 | Cherry picker (MEWP) | Moor Lane | 0.012 |  |  | 48 | 30 | 1440 | 4449.6 | 1296 | 7185.6 | 2.99
27.140 | Overhead, Moor Lane pole route | Catenary wire and pole fittings | 2400 | m | Overhead linesman | 0.01 |  | 1.4 | 0 |  | Moor Lane |  |  |  | 24 | 30 | 720 | 3360 | 0 | 4080 | 1.7
27.110 | Overhead, Moor Lane pole route | Option 1: fibre in new duct in place of overhead, north end | 600 | m | Labourer | 0.15 |  | 5.23 | 3 | Mini digger | Moor Lane | 0.05 | Yes |  | 90 | 22 | 1980 | 3232.14 | 540 | 5752.14 | 9.59
27.100 | Overhead, Moor Lane pole route | Overhead fibre over the A-road, night working | 120 | m | Overhead linesman | 0.05 | 45 | 1.8 | 3 | Cherry picker (MEWP) | Moor Lane | 0.03 |  |  | 6 | 45 | 270 | 222.48 | 162 | 654.48 | 5.45
27.180 | Overhead, Moor Lane pole route | Stays and anchors | 14 | nr | Overhead linesman | 1.5 |  | 52.3 | 0 | Cherry picker (MEWP) | Moor Lane | 0.5 |  |  | 21 | 30 | 630 | 732.2 | 315 | 1677.2 | 119.8
27.170 | Overhead, Moor Lane pole route | Overhead slack coils on storage brackets | 10 | nr | Overhead linesman | 1 |  | 35.8 | 0 | Cherry picker (MEWP) | Moor Lane | 0.5 |  |  | 10 | 30 | 300 | 358 | 225 | 883 | 88.3
27.180 | Overhead, Moor Lane pole route | Pole risers and guards at transitions | 4 | nr | Overhead linesman | 2 |  | 66 | 0 |  | Moor Lane |  |  |  | 8 | 30 | 240 | 264 | 0 | 504 | 126
27.200 | Building lead-ins | Lead-in trench and 32 mm duct, chamber to building | 360 | m | Labourer | 0.12 |  | 3.41 | 3 | Mini digger | Units 1 to 12 | 0.04 |  |  | 43.2 | 22 | 950.4 | 1264.43 | 259.2 | 2474.03 | 6.87
27.110 | Building lead-ins | Drop cable, 12-fibre, pulled to buildings | 420 | m | Fibre technician | 0.012 |  | 0.88 | 5 | Cable winch, trailer-mounted | Units 1 to 12 | 0.004 |  |  | 5.04 | 27 | 136.08 | 388.08 | 33.6 | 557.76 | 1.33
27.200 | Building lead-ins | Wall-mounted fibre termination boxes | 12 | nr | Fibre technician | 2 |  | 102 | 0 |  | Units 1 to 12 |  |  |  | 24 | 27 | 648 | 1224 | 0 | 1872 | 156
27.200 | Building lead-ins | Core and seal building entries | 12 | nr | Labourer | 1 |  | 19.3 | 0 |  | Units 1 to 12 |  |  |  | 12 | 22 | 264 | 231.6 | 0 | 495.6 | 41.3
27.210 | Jointing and testing | Fusion splices | 432 | nr | Fibre jointer | 0.08 |  | 0.66 | 0 |  | Street cabinet |  |  |  | 34.56 | 30 | 1036.8 | 285.12 | 0 | 1321.92 | 3.06
27.210 | Jointing and testing | Joint closures, prepared and mounted | 4 | nr | Fibre jointer | 4 |  | 420 | 0 |  | Park Way |  |  |  | 16 | 30 | 480 | 1680 | 0 | 2160 | 540
27.210 | Jointing and testing | Exchange patch panel, 144-port, terminated | 1 | nr | Fibre technician | 16 |  | 1320 | 0 |  | Street cabinet |  |  |  | 16 | 27 | 432 | 1320 | 0 | 1752 | 1752
27.210 | Jointing and testing | Splice cassettes and pigtails at the cabinet | 144 | nr | Fibre technician | 0.05 |  | 3.58 | 0 |  | Street cabinet |  |  |  | 7.2 | 27 | 194.4 | 515.52 | 0 | 709.92 | 4.93
27.220 | Jointing and testing | OTDR and insertion loss testing, per fibre | 288 | nr | Fibre jointer | 0.05 |  | 0 | 0 |  | Street cabinet |  |  |  | 14.4 | 30 | 432 | 0 | 0 | 432 | 1.5
27.180 | General | Transfer existing attachments for clearance | 18 | nr | Overhead linesman | 1.2 |  | 13.8 | 0 | Cherry picker (MEWP) | Moor Lane | 0.8 |  |  | 21.6 | 30 | 648 | 248.4 | 648 | 1544.4 | 85.8
27.190 | General | Marker posts along buried route | 30 | nr | Labourer | 0.3 |  | 15.4 | 0 |  | Park Way |  |  |  | 9 | 22 | 198 | 462 | 0 | 660 | 22
27.230 | General | Cable labels at poles and chambers | 70 | nr | Labourer | 0.15 |  | 3.3 | 0 |  | Moor Lane |  |  |  | 10.5 | 22 | 231 | 231 | 0 | 462 | 6.6
27.240 | General | As-built drawings and fibre records | 1 | item | Fibre technician | 24 |  | 0 | 0 |  | Street cabinet |  |  |  | 24 | 27 | 648 | 0 | 0 | 648 | 648
[11 empty] | Totals, lines counted |  |  |  | 499.2 |  | 13397.58 | 37880.63 | 3082.8 | 54361.01
[11 empty] | Total of lines left out (Excluded = Yes) | [8 empty] | 5752.14
Note on B6: Your cost code, for example 09.100. Pick one from the Codes tab, or type your own. Optional.
Note on C6: Groups lines, for example a floor or a phase. Optional.
Note on D6: What the line is. Optional but useful.
Note on E6: How much, in the unit next to it. Use a minus sign for a credit.
Note on F6: For example m2, SF, LF, ea.
Note on G6: Who does the work. Pick from your list on the Rates tab. Leave blank for the standard rate.
Note on H6: Hours of work for one unit.
Note on I6: Only if this one line has its own hourly rate. Leave blank to use the trade's rate. A typed 0 counts as a rate of 0.
Note on J6: Material cost for one unit.
Note on K6: Allowance for waste, for example 5 for 5%.
Note on L6: Pick from your list on the Rates tab. Optional.
Note on M6: A room or zone, for information. Optional.
Note on N6: Only if the plant runs for a different number of hours than the crew. Leave blank to use the crew's hours. A typed 0 counts as 0.
Note on O6: Pick Yes to price the line but leave it out of every total, for example an option the owner has not decided on.
Note on P6: Anything you want to remember about the line. Not used in any sum.
Note on Q6: Quantity x hours per unit.
Note on R6: The line's own rate if it has one, otherwise the trade's rate, otherwise the standard rate.
Note on S6: Line hours x hourly rate, rounded to the penny.
Note on T6: Quantity x material price x (1 + waste %), rounded to the penny.
Note on U6: Hours x the plant rate, rounded to the penny. The hours are the crew's unless you typed plant hours.
Note on V6: Labour + materials + plant.
Note on W6: Line total divided by the quantity, rounded to the penny. For information only.
Note on X6: A plain note if something on the line needs a look.
Note on V69: What the lines marked Excluded come to. For information only: it is added to nothing.

## Subcontractors
Free estimating spreadsheet from Bidfident
Subcontractors
One row for each package of work you let to a subcontractor. Type up to four quotes. The lowest quote is carried unless you pick another by number. No quotes yet? Type an allowance and it is carried until a quote comes in.
You type | [13 empty] | Worked out for you
Cost code | Package | In the tender? | Quote 1 from | Amount | Quote 2 from | Amount | Quote 3 from | Amount | Quote 4 from | Amount | Use quote no. | Allowance | Notes | Lowest quote | Quote carried | Carried from | Amount | In the tender
01.210 | Utility survey and cable tracing | Yes | Bidder A | 2100 | Bidder B | 1850 | Bidder C | [5 empty] | Bidder C: Declined | 1850 | 2 | Bidder B | 1850 | 1850
27.120 | Directional drilling under the brook | Yes | Bidder A | 5170 | Bidder B | 4895 | Bidder C | 5610 |  |  |  |  | Bidder A: Incl. 50 mm duct | 4895 | 2 | Bidder B | 4895 | 4895
27.180 | Pole owner make-ready works, allowance | Yes | [9 empty] | 4400 |  |  |  | Allowance | 4400 | 4400
[16 empty] | Total in the tender |  | 11145
Note on C6: Type a name to start a package, for example Firestopping.
Note on D6: Leave blank or Yes to count the package. No leaves it out of the tender but keeps its figures.
Note on M6: Leave blank to carry the lowest quote. Type 1, 2, 3 or 4 to carry that quote instead.
Note on N6: Carried only when there are no quotes yet.
Note on P6: The lowest quote above zero.
Note on Q6: Which quote is carried (1 to 4). The lowest unless you picked another.
Note on S6: The carried quote, or the allowance when there are no quotes.
Note on T6: What goes into the tender: the amount, or 0 if the package is switched off.

## Preliminaries
Free estimating spreadsheet from Bidfident
Preliminaries
Running costs that are not tied to one line of work: supervision, site office, small tools, bins. Weekly and monthly items can follow the job length from the Rates tab, so they grow if the job runs longer.
You type | [5 empty] | Worked out for you
Cost code | Description | Unit | Follows job length? | Quantity | Rate | Quantity used | Amount
01.100 | Site supervisor | wk | Yes |  | 900 | 5 | 4500
27.270 | Traffic management | wk | Yes |  | 950 | 5 | 4750
01.100 | Contracts manager, part time | mo | Yes |  | 1430 | 1.1538 | 1650
01.190 | Street works notices and pole attachment fees | LS |  | 1 | 1210 | 1 | 1210
01.110 | Mobilise gangs and plant | LS |  | 1 | 1380 | 1 | 1380
[5 empty] | Total |  | 13490
Note on D6: wk = per week, mo = per month, day, hr, LS = lump sum, ea = each.
Note on E6: Yes makes a weekly (wk) or monthly (mo) item follow the job length on the Rates tab. Other units ignore it.
Note on F6: How many, when the item does not follow the job length.
Note on H6: The quantity that is used: the job length (in weeks, or in months = weeks divided by 52 over 12) for items that follow it, otherwise what you typed.
Note on I6: Quantity used x rate, rounded to the penny.

## Tender summary
Free estimating spreadsheet from Bidfident
Tender summary
Your tender, worked out in the order the calculations run. Each amount is rounded to the penny where it is worked out, so the column adds up exactly. Nothing on this tab is typed: change the other tabs and it follows.
Job | Business park fibre (example)
Location ¦ Tender due ¦ Length | Near Malton, North Yorkshire ¦ 20/11/2026 ¦ 5 weeks
Item | Amount | How it is worked out
Own work | 54361.01 | The lines on the Estimate tab, apart from any marked Excluded.
Labour | 13397.58
Materials | 37880.63
Plant | 3082.8
Subcontractors | 11145 | The quote carried for each package, or its allowance.
Preliminaries | 13490 | From the Preliminaries tab.
Direct cost | 78996.01 | Own work + subcontractors + preliminaries
Contingency | 2369.88 | 3% of direct cost
Overheads and profit | 8136.59 | 10% of direct cost plus contingency
Subtotal before the bond | 89502.48 | Direct cost + contingency + overheads and profit.
Bond | 895.02 | 1% of the subtotal
Insurance | 447.51 | 0.5% of the subtotal
Tender total | 90845.01 | The price you tender, before VAT.
VAT, for reference | 18169 | 20%, shown separately and not part of the tender total
Tender total including VAT | 109014.01 | For reference.
Left out of the tender (Excluded lines) | 5752.14 | Priced so you can see them, added to nothing.
Lines that need a look | 0 | Every line has what it needs.
When your spreadsheet gets heavy
Bidfident does these same sums on a page, and adds what a spreadsheet cannot do:
Every tender in one place, with saved versions you can compare with now and restore.
Totals by cost code and by area, worked out for you.
It can read the Estimate tab of this spreadsheet, so your lines come across.
See it on an example job:
See Bidfident | bidfident.com/uk

## Quotation
Quotation
Date | 2026-11-20
Valid for (days) | 30
Valid until | 2026-12-20
Reference | Q-0001
From
Your business | Sample Fibre Cabling Ltd
Contact | Name, phone and email
Address | Street, town, postcode
To
Customer | Sample Customer
Address | Street, town, postcode
Job
Job | Business park fibre (example)
Location | Near Malton, North Yorkshire
Expected length | 5 weeks
Scope of work
The fibre cabling work listed in our estimate, including materials, labour and plant. Work areas left clean and tidy at the end of each day.
Not included
Anything not listed above. Work by other trades, permits and fees, unless stated above.
Price
Price |  | 90845.01
VAT at 20% |  | 18169
Total including VAT |  | 109014.01
Terms
Payment: 30% on acceptance, the balance within 14 days of completion. This price holds until the date above. Changes to the scope are priced before the work starts.
Acceptance
Signed for the customer
| Name and signature | Date
Signed for Sample Fibre Cabling Ltd
| Name and signature | Date
Prepared with a free estimating spreadsheet from Bidfident, bidfident.com
Note on C3: This page goes to your customer, so its boxes are white, not yellow. Type in the boxes down the page; the job and the price come from the other tabs. Print it or save it as a PDF.
Note on C18: From the Rates tab.
Note on C19: From the Rates tab.
Note on C20: From the Rates tab.
Note on D31: The price is worked out on the Tender summary tab and cannot be typed over here.

## Codes
Free estimating spreadsheet from Bidfident
Starter cost codes
Bidfident's own starter list for fibre cabling, with the 01 codes for site set-up and running costs: one code for each kind of work you price. Pick one in the Cost code column on the Estimate tab, or type your own. Every code starts with a two-digit number, which is how Bidfident groups an estimate. Change the list to suit your business: rename, delete, or add codes between the numbers.
Codes
Code | Description | Unit
01.100 | Site management | wk
01.110 | Setting up and clearing the site | item
01.120 | Site cabin and storage | wk
01.130 | Temporary power and lighting | wk
01.140 | Temporary heating and ventilation | wk
01.150 | Welfare facilities | wk
01.160 | Hoarding and signs | item
01.170 | Health and safety plan and training | item
01.180 | Protective gear and first aid | item
01.190 | Permits and fees | item
01.200 | Insurance and bonds | item
01.210 | Setting out and surveying | day
01.220 | Scaffold and access equipment | wk
01.230 | Crane and deliveries | day
01.240 | Skips and waste removal | nr
01.250 | Daily cleaning | wk
01.260 | Final clean | item
01.270 | Protection of existing floors and finishes | item
01.280 | Site vehicles and fuel | item
01.290 | Small tools and supplies | item
01.300 | Drawings and samples | item
01.310 | Testing and inspections | item
01.320 | Handover documents and manuals | item
01.330 | Defects period and call backs | item
01.340 | Provisional sums | item
01.350 | Overtime and premium time | hr
01.360 | Weather protection | item
01.370 | Meetings and site paperwork | hr
27.100 | Aerial cable on poles | m
27.110 | Cable pulled in duct | m
27.120 | Direct buried cable | m
27.130 | Building riser cable | m
27.140 | Strand and lashing | m
27.150 | Cable blowing | m
27.160 | Handholes and pull boxes | nr
27.170 | Slack loops and storage | nr
27.180 | Pole attachments and hardware | nr
27.190 | Tracer wire and markers | m
27.200 | Building entrance work | nr
27.210 | Patch panels and enclosures | nr
27.220 | Optical testing per strand | nr
27.230 | Labels and cable tags | item
27.240 | As built and test records | item
27.250 | Cherry picker and crew | day
27.260 | Cable puller and trailer | day
27.270 | Permits and traffic control | item
27.280 | Daywork | hr
Free to use for your own bids. Change it to suit your business. Please don't resell it or hand it out as your own list.
Bidfident's own starter list, version 1, October 2026. Not affiliated with or endorsed by CSI, CSC or RICS.