## Start here
Free estimating spreadsheet from Bidfident
Fiber runs: estimate
United States version, with a worked example
Version 0.1, October 2026. The latest copy is at bidfident.com.
What this is
A ready-to-use estimating spreadsheet for fiber runs. Price your work line by line, compare subcontractor quotes, add your running costs and profit, and get a bid total that adds up to the cent. Every figure is worked out by a formula, so change a rate or a quantity and everything follows.
This copy | This copy is filled in with a worked example: fiber to a rural business park, Boone County, MO. It is a made-up job with realistic figures, so you can see how it all fits. Change any yellow cell and watch the bid change. The blank copy has the same layout, empty.
How to use it, in five steps
1 Rates | Type your hourly rates for each trade and each piece of equipment, the job length in weeks, and your percentages (contingency, fee, bond, insurance, sales tax).
2 Estimate | One row for each line of work. Type the quantity, the hours each unit takes and what the materials cost. Pick the trade and equipment from the lists, and a cost code from the Codes tab, or type your own. Mark a line Excluded to price it without counting it, for example an option. A line that needs a look turns pink.
3 Subcontractors and general conditions | On the Subcontractors tab, type the quotes you have for each package. The lowest is carried unless you pick another. On the General conditions tab, add running costs; weekly and monthly ones follow the job length.
4 Bid summary | Your bid total, worked out in order: direct cost, contingency, fee, bond, insurance. Nothing to type here.
5 Quote | A one-page quote to send to your customer. Type your details, the scope and what is not included; the price comes from the Bid summary tab. Print it or save it as a PDF.
Which cells are which
Yellow | You type here.
Grey | Worked out for you. These cells are locked so a formula cannot be typed over by accident.
How the figures are worked out
Labor = hours x hourly rate. Materials = quantity x price x (1 + waste %). Equipment = hours x its rate. Each of those is rounded to the cent, half up, and a line is their sum. Quantities, hours and rates are never rounded, and totals add up the rounded amounts, so every column adds up exactly. Then: direct cost = own work + subcontractors + general conditions. Contingency is a percentage of the direct cost, fee of direct cost plus contingency. Bond and insurance are each a percentage of the subtotal before them (not of each other). Sales tax is shown beside the bid total and is not part of it.
Good to know
Locked cells | Only the yellow cells, and the boxes on the Quote, can be typed in. To change a formula, unprotect the sheet. In Excel: Review, then Unprotect Sheet (there is no password). In Google Sheets: Data, then Protect sheets and ranges, then remove the protection.
Room | There is room for 60 lines, 8 packages and 12 running costs. For a bigger job, use a second copy for part of the work.
Check before you send | This is a tool for your own estimating. Check every figure before you send a bid. Free to use for your own bids; please do not resell it.
When your spreadsheet gets heavy
If you end up with lots of bids, changing rates, or more than one person working on them, Bidfident does the same sums on a page, keeps every bid with its saved versions, and totals by cost code and area. You can try it on an example job first. It can read the Estimate tab of this spreadsheet, so your lines come across.
See Bidfident | bidfident.com/us

## Rates
Free estimating spreadsheet from Bidfident
Rates and job details
Type your rates here once. Every line on the Estimate tab picks them up, so changing a rate here changes the whole bid. Yellow cells are for you.
Job details
Job name | Business park fiber (example) | Shown on the Bid summary tab.
Location | Boone County, MO
Bid due | 2026-11-20
Job length (weeks) | 5 | Weekly and monthly items on the General conditions tab follow this.
Labor rates
Trade | Rate per hour ($) | Pick the trade by this name in the Trade column on the Estimate tab.
Fiber technician | 60
Lineman | 66
Laborer | 45
Splicer | 64
Standard rate (lines with no trade picked) | 58 | Used for a line that has hours but no trade, or a trade that is not on this list.
Equipment rates
Equipment | Rate per hour ($) | Pick it by this name in the Equipment column on the Estimate tab.
Bucket truck | 75
Mini excavator | 65
Cable puller, trailer-mounted | 40
Percentages (type 3 for 3%)
Contingency (%) | 3 | Added to the direct cost, for what you cannot yet see.
Fee (%) | 10 | Your profit, added to the direct cost plus contingency.
Bond (%) | 1 | Taken from the subtotal. Leave at 0 if you are not bonded.
Insurance (%) | 0.5 | Taken from the same subtotal as bond, not from each other.
Sales tax (%) | 0 | Shown for reference, apart from the bid total. Starts at 0: type your own state or local rate if you want it shown.

## Estimate
Free estimating spreadsheet from Bidfident
Fiber runs: estimate
One row per line of work. Type in the yellow cells; the grey cells are worked out for you. Hours, labour, materials and equipment are each rounded to the cent, so every column adds up exactly. Hold your pointer over a heading for what it means.
You type | [14 empty] | Worked out for you
Cost code | Area | Description | Qty | Unit | Trade | Hrs/unit | Rate override | Mat $/unit | Waste % | Equipment | Location | Equip hrs/unit | Excluded | Notes | Line hours | Hourly rate used | Cost of labour | Cost of materials | Cost of equipment | Line total | Line price per unit | Check this line
27 110 | Underground, Park Drive | Fiber cable, 144-count, pulled in conduit | 20350 | LF | Fiber technician | 0.0025 |  | 1.05 | 3 |  | Park Drive |  |  |  | 50.875 | 60 | 3052.5 | 22008.53 | 0 | 25061.03 | 1.23
27 160 | Underground, Park Drive | Handholes, set and backfilled | 12 | ea | Laborer | 3 |  | 520 | 0 |  | Park Drive |  |  |  | 36 | 45 | 1620 | 6240 | 0 | 7860 | 655
27 170 | Underground, Park Drive | Slack loops and storage brackets | 18 | ea | Fiber technician | 0.75 |  | 36 | 0 |  | Park Drive |  |  |  | 13.5 | 60 | 810 | 648 | 0 | 1458 | 81
27 110 | Underground, Park Drive | Prove existing conduit with mandrel and pull tape | 20350 | LF | Laborer | 0.000914 |  | 0.04 | 0 |  | Park Drive |  |  |  | 18.5999 | 45 | 837 | 814 | 0 | 1651 | 0.08
27 110 | Underground, Park Drive | Conduit repairs at blockages, dig and couple | 4 | ea | Laborer | 6 |  | 144 | 0 | Mini excavator | Park Drive | 2 |  |  | 24 | 45 | 1080 | 576 | 520 | 2176 | 544
27 160 | Underground, Park Drive | Traffic-rated handhole lids at driveway crossings | 3 | ea | Laborer | 1 |  | 336 | 0 |  | Park Drive |  |  |  | 3 | 45 | 135 | 1008 | 0 | 1143 | 381
27 140 | Aerial, County Road 12 pole line | Aerial fiber, lashed to strand | 7875 | LF | Lineman | 0.006 |  | 0.95 | 3 | Bucket truck | County Road 12 | 0.004 |  |  | 47.25 | 66 | 3118.5 | 7705.69 | 2362.5 | 13186.69 | 1.67
27 140 | Aerial, County Road 12 pole line | Strand and pole hardware | 7875 | LF | Lineman | 0.003 |  | 0.52 | 0 |  | County Road 12 |  |  |  | 23.625 | 66 | 1559.25 | 4095 | 0 | 5654.25 | 0.72
27 110 | Aerial, County Road 12 pole line | Alternate 1: fiber in new conduit in place of aerial, north end | 1970 | LF | Laborer | 0.0457 |  | 2.32 | 3 | Mini excavator | County Road 12 | 0.0152 | Yes |  | 90.029 | 45 | 4051.31 | 4707.51 | 1946.36 | 10705.18 | 5.43
27 100 | Aerial, County Road 12 pole line | Aerial fiber over State Route 7, lashed at night | 394 | LF | Lineman | 0.0152 | 99 | 0.95 | 3 | Bucket truck | County Road 12 | 0.00914 |  |  | 5.9888 | 99 | 592.89 | 385.53 | 270.09 | 1248.51 | 3.17
27 180 | Aerial, County Road 12 pole line | Down guys and anchors | 14 | ea | Lineman | 1.5 |  | 76 | 0 | Bucket truck | County Road 12 | 0.5 |  |  | 21 | 66 | 1386 | 1064 | 525 | 2975 | 212.5
27 170 | Aerial, County Road 12 pole line | Aerial slack loops on snowshoes | 10 | ea | Lineman | 1 |  | 52 | 0 | Bucket truck | County Road 12 | 0.5 |  |  | 10 | 66 | 660 | 520 | 375 | 1555 | 155.5
27 180 | Aerial, County Road 12 pole line | U-guard risers at pole transitions | 4 | ea | Lineman | 2 |  | 96 | 0 |  | County Road 12 |  |  |  | 8 | 66 | 528 | 384 | 0 | 912 | 228
27 200 | Building laterals | Lateral trench and 1-1/2" conduit, handhole to building | 1180 | LF | Laborer | 0.0366 |  | 1.51 | 3 | Mini excavator | Lots 1 to 12 | 0.0122 |  |  | 43.188 | 45 | 1943.46 | 1835.25 | 935.74 | 4714.45 | 4
27 110 | Building laterals | Drop cable, 12-count, pulled to buildings | 1380 | LF | Fiber technician | 0.00366 |  | 0.39 | 5 | Cable puller, trailer-mounted | Lots 1 to 12 | 0.00122 |  |  | 5.0508 | 60 | 303.05 | 565.11 | 67.34 | 935.5 | 0.68
27 200 | Building laterals | Wall-mount fiber terminals at buildings | 12 | ea | Fiber technician | 2 |  | 148 | 0 |  | Lots 1 to 12 |  |  |  | 24 | 60 | 1440 | 1776 | 0 | 3216 | 268
27 200 | Building laterals | Core and seal building entries | 12 | ea | Laborer | 1 |  | 28 | 0 |  | Lots 1 to 12 |  |  |  | 12 | 45 | 540 | 336 | 0 | 876 | 73
27 210 | Splicing and testing | Fusion splices | 432 | ea | Splicer | 0.08 |  | 0.96 | 0 |  | Hub shelter |  |  |  | 34.56 | 64 | 2211.84 | 414.72 | 0 | 2626.56 | 6.08
27 210 | Splicing and testing | Splice cases, prepped and mounted | 4 | ea | Splicer | 4 |  | 620 | 0 |  | Park Drive |  |  |  | 16 | 64 | 1024 | 2480 | 0 | 3504 | 876
27 210 | Splicing and testing | Hub patch panel, 144-port, terminated | 1 | ea | Fiber technician | 16 |  | 1920 | 0 |  | Hub shelter |  |  |  | 16 | 60 | 960 | 1920 | 0 | 2880 | 2880
27 210 | Splicing and testing | Splice trays and pigtails at the hub | 144 | ea | Fiber technician | 0.05 |  | 5.2 | 0 |  | Hub shelter |  |  |  | 7.2 | 60 | 432 | 748.8 | 0 | 1180.8 | 8.2
27 220 | Splicing and testing | OTDR and power meter testing, per fiber | 288 | ea | Splicer | 0.05 |  | 0 | 0 |  | Hub shelter |  |  |  | 14.4 | 64 | 921.6 | 0 | 0 | 921.6 | 3.2
27 180 | General | Transfer existing attachments for clearance | 18 | ea | Lineman | 1.2 |  | 20 | 0 | Bucket truck | County Road 12 | 0.8 |  |  | 21.6 | 66 | 1425.6 | 360 | 1080 | 2865.6 | 159.2
27 190 | General | Route markers along buried route | 30 | ea | Laborer | 0.3 |  | 22.4 | 0 |  | Park Drive |  |  |  | 9 | 45 | 405 | 672 | 0 | 1077 | 35.9
27 230 | General | Cable tags at poles and handholes | 70 | ea | Laborer | 0.15 |  | 4.8 | 0 |  | County Road 12 |  |  |  | 10.5 | 45 | 472.5 | 336 | 0 | 808.5 | 11.55
27 240 | General | As-built drawings and fiber records | 1 | LS | Fiber technician | 24 |  | 0 | 0 |  | Hub shelter |  |  |  | 24 | 60 | 1440 | 0 | 0 | 1440 | 1440
[11 empty] | Totals, lines counted |  |  |  | 499.3375 |  | 28898.19 | 56892.63 | 6135.67 | 91926.49
[11 empty] | Total of lines left out (Excluded = Yes) | [8 empty] | 10705.18
Note on B6: Your cost code, for example 09 100. Pick one from the Codes tab, or type your own. Optional.
Note on C6: Groups lines, for example a floor or a phase. Optional.
Note on D6: What the line is. Optional but useful.
Note on E6: How much, in the unit next to it. Use a minus sign for a credit.
Note on F6: For example m2, SF, LF, ea.
Note on G6: Who does the work. Pick from your list on the Rates tab. Leave blank for the standard rate.
Note on H6: Hours of work for one unit.
Note on I6: Only if this one line has its own hourly rate. Leave blank to use the trade's rate. A typed 0 counts as a rate of 0.
Note on J6: Material cost for one unit.
Note on K6: Allowance for waste, for example 5 for 5%.
Note on L6: Pick from your list on the Rates tab. Optional.
Note on M6: A room or zone, for information. Optional.
Note on N6: Only if the equipment runs for a different number of hours than the crew. Leave blank to use the crew's hours. A typed 0 counts as 0.
Note on O6: Pick Yes to price the line but leave it out of every total, for example an option the owner has not decided on.
Note on P6: Anything you want to remember about the line. Not used in any sum.
Note on Q6: Quantity x hours per unit.
Note on R6: The line's own rate if it has one, otherwise the trade's rate, otherwise the standard rate.
Note on S6: Line hours x hourly rate, rounded to the cent.
Note on T6: Quantity x material price x (1 + waste %), rounded to the cent.
Note on U6: Hours x the equipment rate, rounded to the cent. The hours are the crew's unless you typed equipment hours.
Note on V6: Labour + materials + equipment.
Note on W6: Line total divided by the quantity, rounded to the cent. For information only.
Note on X6: A plain note if something on the line needs a look.
Note on V69: What the lines marked Excluded come to. For information only: it is added to nothing.

## Subcontractors
Free estimating spreadsheet from Bidfident
Subcontractors
One row for each package of work you let to a subcontractor. Type up to four quotes. The lowest quote is carried unless you pick another by number. No quotes yet? Type an allowance and it is carried until a quote comes in.
You type | [13 empty] | Worked out for you
Cost code | Package | In the bid? | Quote 1 from | Amount | Quote 2 from | Amount | Quote 3 from | Amount | Quote 4 from | Amount | Use quote no. | Allowance | Notes | Lowest quote | Quote carried | Carried from | Amount | In the bid
01 210 | Utility locates | Yes | Bidder A | 2900 | Bidder B | 2500 | Bidder C | [5 empty] | Bidder C: Declined | 2500 | 2 | Bidder B | 2500 | 2500
27 120 | Directional bore at the creek crossing | Yes | Bidder A | 7520 | Bidder B | 7120 | Bidder C | 8160 |  |  |  |  | Bidder A: Incl. 2" conduit | 7120 | 2 | Bidder B | 7120 | 7120
27 180 | Pole owner make-ready, allowance | Yes | [9 empty] | 6400 |  |  |  | Allowance | 6400 | 6400
[16 empty] | Total in the bid |  | 16020
Note on C6: Type a name to start a package, for example Firestopping.
Note on D6: Leave blank or Yes to count the package. No leaves it out of the bid but keeps its figures.
Note on M6: Leave blank to carry the lowest quote. Type 1, 2, 3 or 4 to carry that quote instead.
Note on N6: Carried only when there are no quotes yet.
Note on P6: The lowest quote above zero.
Note on Q6: Which quote is carried (1 to 4). The lowest unless you picked another.
Note on S6: The carried quote, or the allowance when there are no quotes.
Note on T6: What goes into the bid: the amount, or 0 if the package is switched off.

## General conditions
Free estimating spreadsheet from Bidfident
General conditions
Running costs that are not tied to one line of work: supervision, site office, small tools, bins. Weekly and monthly items can follow the job length from the Rates tab, so they grow if the job runs longer.
You type | [5 empty] | Worked out for you
Cost code | Description | Unit | Follows job length? | Quantity | Rate | Quantity used | Amount
01 100 | Supervision, foreman | wk | Yes |  | 1350 | 5 | 6750
27 270 | Traffic control | wk | Yes |  | 1100 | 5 | 5500
01 100 | Project manager, part time | mo | Yes |  | 2080 | 1.1538 | 2400
01 190 | Right-of-way and pole attachment permits | LS |  | 1 | 1760 | 1 | 1760
01 110 | Mobilize crews and equipment | LS |  | 1 | 2000 | 1 | 2000
[5 empty] | Total |  | 18410
Note on D6: wk = per week, mo = per month, day, hr, LS = lump sum, ea = each.
Note on E6: Yes makes a weekly (wk) or monthly (mo) item follow the job length on the Rates tab. Other units ignore it.
Note on F6: How many, when the item does not follow the job length.
Note on H6: The quantity that is used: the job length (in weeks, or in months = weeks divided by 52 over 12) for items that follow it, otherwise what you typed.
Note on I6: Quantity used x rate, rounded to the cent.

## Bid summary
Free estimating spreadsheet from Bidfident
Bid summary
Your bid, worked out in the order the calculations run. Each amount is rounded to the cent where it is worked out, so the column adds up exactly. Nothing on this tab is typed: change the other tabs and it follows.
Job | Business park fiber (example)
Location ¦ Bid due ¦ Length | Boone County, MO ¦ 11/20/2026 ¦ 5 weeks
Item | Amount | How it is worked out
Own work | 91926.49 | The lines on the Estimate tab, apart from any marked Excluded.
Labor | 28898.19
Materials | 56892.63
Equipment | 6135.67
Subcontractors | 16020 | The quote carried for each package, or its allowance.
General conditions | 18410 | From the General conditions tab.
Direct cost | 126356.49 | Own work + subcontractors + general conditions
Contingency | 3790.69 | 3% of direct cost
Fee | 13014.72 | 10% of direct cost plus contingency
Subtotal before the bond | 143161.9 | Direct cost + contingency + fee.
Bond | 1431.62 | 1% of the subtotal
Insurance | 715.81 | 0.5% of the subtotal
Bid total | 145309.33 | The price you submit.
Sales tax, for reference | 0 | 0%, shown separately and not part of the bid total. Set your rate on the Rates tab.
Bid total including sales tax | 145309.33 | For reference.
Left out of the bid (Excluded lines) | 10705.18 | Priced so you can see them, added to nothing.
Lines that need a look | 0 | Every line has what it needs.
When your spreadsheet gets heavy
Bidfident does these same sums on a page, and adds what a spreadsheet cannot do:
Every bid in one place, with saved versions you can compare with now and restore.
Totals by cost code and by area, worked out for you.
It can read the Estimate tab of this spreadsheet, so your lines come across.
See it on an example job:
See Bidfident | bidfident.com/us

## Quote
Quote
Date | 2026-11-20
Valid for (days) | 30
Valid until | 2026-12-20
Reference | Q-0001
From
Your business | Sample Fiber Runs Co.
Contact | Name, phone and email
Address | Street, town, postcode
To
Customer | Sample Customer
Address | Street, town, postcode
Job
Job | Business park fiber (example)
Location | Boone County, MO
Expected length | 5 weeks
Scope of work
The fiber runs work listed in our estimate, including materials, labor and equipment. Work areas left clean and tidy at the end of each day.
Not included
Anything not listed above. Work by other trades, permits and fees, unless stated above.
Price
Price |  | 145309.33
Sales tax is not included
Terms
Payment: 30% on acceptance, the balance within 14 days of completion. This price holds until the date above. Changes to the scope are priced before the work starts.
Acceptance
Signed for the customer
| Name and signature | Date
Signed for Sample Fiber Runs Co.
| Name and signature | Date
Prepared with a free estimating spreadsheet from Bidfident, bidfident.com
Note on C3: This page goes to your customer, so its boxes are white, not yellow. Type in the boxes down the page; the job and the price come from the other tabs. Print it or save it as a PDF.
Note on C18: From the Rates tab.
Note on C19: From the Rates tab.
Note on C20: From the Rates tab.
Note on D31: The price is worked out on the Bid summary tab and cannot be typed over here.

## Codes
Free estimating spreadsheet from Bidfident
Starter cost codes
Bidfident's own starter list for fiber runs, with the 01 codes for site set-up and running costs: one code for each kind of work you price. Pick one in the Cost code column on the Estimate tab, or type your own. Every code starts with a two-digit number, which is how Bidfident groups an estimate. Change the list to suit your business: rename, delete, or add codes between the numbers.
Codes
Code | Description | Unit
01 100 | Project management and supervision | wk
01 110 | Mobilization and demobilization | ls
01 120 | Site office and storage | wk
01 130 | Temporary power and lighting | wk
01 140 | Temporary heat and ventilation | wk
01 150 | Washrooms and handwashing | wk
01 160 | Fencing and signs | ls
01 170 | Safety plan and training | ls
01 180 | Safety gear and first aid | ls
01 190 | Permits and fees | ls
01 200 | Insurance and bonds | ls
01 210 | Layout and surveying | day
01 220 | Scaffold and access equipment | wk
01 230 | Hoisting and deliveries | day
01 240 | Dumpsters and waste removal | ea
01 250 | Daily cleaning | wk
01 260 | Final cleaning | ls
01 270 | Protection of existing floors and finishes | ls
01 280 | Site vehicles and fuel | ls
01 290 | Small tools and supplies | ls
01 300 | Drawings and submittals | ls
01 310 | Testing and inspections | ls
01 320 | Handover documents and manuals | ls
01 330 | Warranty and call backs | ls
01 340 | Allowances | ls
01 350 | Overtime and premium time | hr
01 360 | Weather protection | ls
01 370 | Meetings and site paperwork | hr
27 100 | Aerial cable on poles | LF
27 110 | Cable pulled in duct | LF
27 120 | Direct buried cable | LF
27 130 | Building riser cable | LF
27 140 | Strand and lashing | LF
27 150 | Cable blowing | LF
27 160 | Handholes and pull boxes | ea
27 170 | Slack loops and storage | ea
27 180 | Pole attachments and hardware | ea
27 190 | Tracer wire and markers | LF
27 200 | Building entrance work | ea
27 210 | Patch panels and enclosures | ea
27 220 | Optical testing per strand | ea
27 230 | Labels and cable tags | ls
27 240 | As built and test records | ls
27 250 | Bucket truck and crew | day
27 260 | Cable puller and trailer | day
27 270 | Permits and traffic control | ls
27 280 | Extra work by the hour | hr
Free to use for your own bids. Change it to suit your business. Please don't resell it or hand it out as your own list.
Bidfident's own starter list, version 1, October 2026. Not affiliated with or endorsed by CSI, CSC or RICS.