## Start here
Free estimating spreadsheet from Bidfident
Tenant improvements: estimate
United States version, with a worked example
Version 0.1, October 2026. The latest copy is at bidfident.com.
What this is
A ready-to-use estimating spreadsheet for tenant improvements. Price your work line by line, compare subcontractor quotes, add your running costs and profit, and get a bid total that adds up to the cent. Every figure is worked out by a formula, so change a rate or a quantity and everything follows.
This copy | This copy is filled in with a worked example: a 3,000 SF retail tenant improvement, Scottsdale, AZ. It is a made-up job with realistic figures, so you can see how it all fits. Change any yellow cell and watch the bid change. The blank copy has the same layout, empty.
How to use it, in five steps
1 Rates | Type your hourly rates for each trade and each piece of equipment, the job length in weeks, and your percentages (contingency, fee, bond, insurance, sales tax).
2 Estimate | One row for each line of work. Type the quantity, the hours each unit takes and what the materials cost. Pick the trade and equipment from the lists, and a cost code from the Codes tab, or type your own. Mark a line Excluded to price it without counting it, for example an option. A line that needs a look turns pink.
3 Subcontractors and general conditions | On the Subcontractors tab, type the quotes you have for each package. The lowest is carried unless you pick another. On the General conditions tab, add running costs; weekly and monthly ones follow the job length.
4 Bid summary | Your bid total, worked out in order: direct cost, contingency, fee, bond, insurance. Nothing to type here.
5 Quote | A one-page quote to send to your customer. Type your details, the scope and what is not included; the price comes from the Bid summary tab. Print it or save it as a PDF.
Which cells are which
Yellow | You type here.
Grey | Worked out for you. These cells are locked so a formula cannot be typed over by accident.
How the figures are worked out
Labor = hours x hourly rate. Materials = quantity x price x (1 + waste %). Equipment = hours x its rate. Each of those is rounded to the cent, half up, and a line is their sum. Quantities, hours and rates are never rounded, and totals add up the rounded amounts, so every column adds up exactly. Then: direct cost = own work + subcontractors + general conditions. Contingency is a percentage of the direct cost, fee of direct cost plus contingency. Bond and insurance are each a percentage of the subtotal before them (not of each other). Sales tax is shown beside the bid total and is not part of it.
Good to know
Locked cells | Only the yellow cells, and the boxes on the Quote, can be typed in. To change a formula, unprotect the sheet. In Excel: Review, then Unprotect Sheet (there is no password). In Google Sheets: Data, then Protect sheets and ranges, then remove the protection.
Room | There is room for 60 lines, 8 packages and 12 running costs. For a bigger job, use a second copy for part of the work.
Check before you send | This is a tool for your own estimating. Check every figure before you send a bid. Free to use for your own bids; please do not resell it.
When your spreadsheet gets heavy
If you end up with lots of bids, changing rates, or more than one person working on them, Bidfident does the same sums on a page, keeps every bid with its saved versions, and totals by cost code and area. You can try it on an example job first. It can read the Estimate tab of this spreadsheet, so your lines come across.
See Bidfident | bidfident.com/us

## Rates
Free estimating spreadsheet from Bidfident
Rates and job details
Type your rates here once. Every line on the Estimate tab picks them up, so changing a rate here changes the whole bid. Yellow cells are for you.
Job details
Job name | Retail store tenant improvement (example) | Shown on the Bid summary tab.
Location | Scottsdale, AZ
Bid due | 2026-11-27
Job length (weeks) | 5 | Weekly and monthly items on the General conditions tab follow this.
Labor rates
Trade | Rate per hour ($) | Pick the trade by this name in the Trade column on the Estimate tab.
Carpenter | 62
Finish carpenter | 62
Flooring installer | 52
Painter | 52
Laborer | 45
Standard rate (lines with no trade picked) | 55 | Used for a line that has hours but no trade, or a trade that is not on this list.
Equipment rates
Equipment | Rate per hour ($) | Pick it by this name in the Equipment column on the Estimate tab.
Scissor lift | 25
Floor grinder | 38
Percentages (type 3 for 3%)
Contingency (%) | 5 | Added to the direct cost, for what you cannot yet see.
Fee (%) | 12 | Your profit, added to the direct cost plus contingency.
Bond (%) | 1 | Taken from the subtotal. Leave at 0 if you are not bonded.
Insurance (%) | 0.5 | Taken from the same subtotal as bond, not from each other.
Sales tax (%) | 0 | Shown for reference, apart from the bid total. Starts at 0: type your own state or local rate if you want it shown.

## Estimate
Free estimating spreadsheet from Bidfident
Tenant improvements: estimate
One row per line of work. Type in the yellow cells; the grey cells are worked out for you. Hours, labour, materials and equipment are each rounded to the cent, so every column adds up exactly. Hold your pointer over a heading for what it means.
You type | [14 empty] | Worked out for you
Cost code | Area | Description | Qty | Unit | Trade | Hrs/unit | Rate override | Mat $/unit | Waste % | Equipment | Location | Equip hrs/unit | Excluded | Notes | Line hours | Hourly rate used | Cost of labour | Cost of materials | Cost of equipment | Line total | Line price per unit | Check this line
06 710 | Interior construction | Metal stud partitions, 3-5/8" studs, drywall both sides | 2200 | SF | Carpenter | 0.07 |  | 2.85 | 8 |  | Back of house |  |  |  | 154 | 62 | 9548 | 6771.6 | 0 | 16319.6 | 7.42
06 720 | Interior construction | Acoustic ceiling, 2 x 4 grid | 2600 | SF | Carpenter | 0.025 |  | 3 | 5 |  | Sales floor |  |  |  | 65 | 62 | 4030 | 8190 | 0 | 12220 | 4.7
06 750 | Interior construction | Luxury vinyl plank | 2700 | SF | Flooring installer | 0.02 |  | 4.5 | 8 |  | Sales floor |  |  |  | 54 | 52 | 2808 | 13122 | 0 | 15930 | 5.9
06 760 | Interior construction | Paint, primer and two coats | 6800 | SF | Painter | 0.008 |  | 0.2 | 5 |  | Sales floor |  |  |  | 54.4 | 52 | 2828.8 | 1428 | 0 | 4256.8 | 0.63
06 730 | Interior construction | Doors, frames and hardware | 7 | ea | Finish carpenter | 4 |  | 800 | 0 |  | Back of house |  |  |  | 28 | 62 | 1736 | 5600 | 0 | 7336 | 1048
06 760 | Interior construction | Alternate 1: slatted wood feature wall | 240 | SF | Finish carpenter | 0.25 |  | 26 | 0 |  | Sales floor |  | Yes |  | 60 | 62 | 3720 | 6240 | 0 | 9960 | 41.5
06 760 | Interior construction | Demising wall, metal stud to deck, after hours | 620 | SF | Carpenter | 0.09 | 93 | 3.4 | 8 | Scissor lift | Back of house | 0.03 |  |  | 55.8 | 93 | 5189.4 | 2276.64 | 465 | 7931.04 | 12.79
06 710 | Interior construction | Metal stud partitions, 3-5/8" studs, drywall both sides | 480 | SF | Carpenter | 0.07 |  | 2.85 | 8 |  | Fitting rooms |  |  |  | 33.6 | 62 | 2083.2 | 1477.44 | 0 | 3560.64 | 7.42
06 730 | Interior construction | Fitting room doors, louvered, with hardware | 6 | ea | Finish carpenter | 2 |  | 340 | 0 |  | Fitting rooms |  |  |  | 12 | 62 | 744 | 2040 | 0 | 2784 | 464
06 750 | Interior construction | Luxury vinyl plank | 220 | SF | Flooring installer | 0.02 |  | 4.5 | 8 |  | Fitting rooms |  |  |  | 4.4 | 52 | 228.8 | 1069.2 | 0 | 1298 | 5.9
06 740 | Interior construction | Drywall soffit at the storefront | 48 | LF | Carpenter | 0.6 |  | 14.5 | 10 | Scissor lift | Sales floor | 0.3 |  |  | 28.8 | 62 | 1785.6 | 765.6 | 360 | 2911.2 | 60.65
06 750 | Interior construction | Porcelain tile floor and base, restroom | 65 | SF | Flooring installer | 0.2 |  | 7.6 | 12 |  | Restroom |  |  |  | 13 | 52 | 676 | 553.28 | 0 | 1229.28 | 18.91
06 720 | Interior construction | Drywall ceiling, restroom | 120 | SF | Carpenter | 0.05 |  | 1.3 | 10 |  | Restroom |  |  |  | 6 | 62 | 372 | 171.6 | 0 | 543.6 | 4.53
06 710 | Interior construction | Fire-rated partition, Type X both sides, electrical room | 240 | SF | Carpenter | 0.08 |  | 3.6 | 8 |  | Back of house |  |  |  | 19.2 | 62 | 1190.4 | 933.12 | 0 | 2123.52 | 8.85
06 720 | Interior construction | Acoustic ceiling, 2 x 4 grid | 300 | SF | Carpenter | 0.025 |  | 3 | 5 |  | Fitting rooms |  |  |  | 7.5 | 62 | 465 | 945 | 0 | 1410 | 4.7
06 760 | Interior construction | Paint, primer and two coats | 2400 | SF | Painter | 0.008 |  | 0.2 | 5 |  | Back of house |  |  |  | 19.2 | 52 | 998.4 | 504 | 0 | 1502.4 | 0.63
06 760 | Interior construction | Paint doors and frames | 13 | ea | Painter | 1.2 |  | 11.2 | 0 |  | Back of house |  |  |  | 15.6 | 52 | 811.2 | 145.6 | 0 | 956.8 | 73.6
06 780 | Interior construction | Rubber base, 4" | 420 | LF | Flooring installer | 0.03 |  | 2.1 | 5 |  | Sales floor |  |  |  | 12.6 | 52 | 655.2 | 926.1 | 0 | 1581.3 | 3.77
06 710 | Interior construction | Access panels in walls and ceilings | 6 | ea | Carpenter | 0.75 |  | 68 | 0 |  | Back of house |  |  |  | 4.5 | 62 | 279 | 408 | 0 | 687 | 114.5
06 750 | Floor prep | Grind and patch slab for vinyl | 2700 | SF | Flooring installer | 0.008 |  | 0.12 | 0 | Floor grinder | Sales floor | 0.005 |  |  | 21.6 | 52 | 1123.2 | 324 | 513 | 1960.2 | 0.73
06 750 | Floor prep | Floor leveling compound, low spots | 800 | SF | Flooring installer | 0.02 |  | 1.3 | 5 |  | Sales floor |  |  |  | 16 | 52 | 832 | 1092 | 0 | 1924 | 2.41
06 710 | Fixtures and backing | Wood blocking for shelving and fixtures | 320 | LF | Carpenter | 0.12 |  | 1.9 | 10 |  | Sales floor |  |  |  | 38.4 | 62 | 2380.8 | 668.8 | 0 | 3049.6 | 9.53
06 760 | Fixtures and backing | Plywood backing, cash wrap and stockroom walls | 160 | SF | Carpenter | 0.03 |  | 2.2 | 10 |  | Back of house |  |  |  | 4.8 | 62 | 297.6 | 387.2 | 0 | 684.8 | 4.28
06 850 | Fixtures and backing | Backing for grab bars and accessories | 8 | ea | Carpenter | 0.5 |  | 9.6 | 0 |  | Restroom |  |  |  | 4 | 62 | 248 | 76.8 | 0 | 324.8 | 40.6
06 750 | Closeout | Floor protection board over new vinyl | 2700 | SF | Laborer | 0.002 |  | 0.22 | 0 |  | Sales floor |  |  |  | 5.4 | 45 | 243 | 594 | 0 | 837 | 0.31
06 760 | Closeout | Paint touch-up after fixture install | 1 | LS | Painter | 24 |  | 144 | 0 |  | Sales floor |  |  |  | 24 | 52 | 1248 | 144 | 0 | 1392 | 1392
06 720 | Closeout | Punch list repairs, drywall and ceilings | 1 | LS | Carpenter | 16 |  | 96 | 0 |  | Sales floor |  |  |  | 16 | 62 | 992 | 96 | 0 | 1088 | 1088
[11 empty] | Totals, lines counted |  |  |  | 717.8 |  | 43793.6 | 50709.98 | 1338 | 95841.58
[11 empty] | Total of lines left out (Excluded = Yes) | [8 empty] | 9960
Note on B6: Your cost code, for example 09 100. Pick one from the Codes tab, or type your own. Optional.
Note on C6: Groups lines, for example a floor or a phase. Optional.
Note on D6: What the line is. Optional but useful.
Note on E6: How much, in the unit next to it. Use a minus sign for a credit.
Note on F6: For example m2, SF, LF, ea.
Note on G6: Who does the work. Pick from your list on the Rates tab. Leave blank for the standard rate.
Note on H6: Hours of work for one unit.
Note on I6: Only if this one line has its own hourly rate. Leave blank to use the trade's rate. A typed 0 counts as a rate of 0.
Note on J6: Material cost for one unit.
Note on K6: Allowance for waste, for example 5 for 5%.
Note on L6: Pick from your list on the Rates tab. Optional.
Note on M6: A room or zone, for information. Optional.
Note on N6: Only if the equipment runs for a different number of hours than the crew. Leave blank to use the crew's hours. A typed 0 counts as 0.
Note on O6: Pick Yes to price the line but leave it out of every total, for example an option the owner has not decided on.
Note on P6: Anything you want to remember about the line. Not used in any sum.
Note on Q6: Quantity x hours per unit.
Note on R6: The line's own rate if it has one, otherwise the trade's rate, otherwise the standard rate.
Note on S6: Line hours x hourly rate, rounded to the cent.
Note on T6: Quantity x material price x (1 + waste %), rounded to the cent.
Note on U6: Hours x the equipment rate, rounded to the cent. The hours are the crew's unless you typed equipment hours.
Note on V6: Labour + materials + equipment.
Note on W6: Line total divided by the quantity, rounded to the cent. For information only.
Note on X6: A plain note if something on the line needs a look.
Note on V69: What the lines marked Excluded come to. For information only: it is added to nothing.

## Subcontractors
Free estimating spreadsheet from Bidfident
Subcontractors
One row for each package of work you let to a subcontractor. Type up to four quotes. The lowest quote is carried unless you pick another by number. No quotes yet? Type an allowance and it is carried until a quote comes in.
You type | [13 empty] | Worked out for you
Cost code | Package | In the bid? | Quote 1 from | Amount | Quote 2 from | Amount | Quote 3 from | Amount | Quote 4 from | Amount | Use quote no. | Allowance | Notes | Lowest quote | Quote carried | Carried from | Amount | In the bid
06 790 | Electrical and lighting | Yes | Bidder A | 19800 | Bidder B | 18400 | [6 empty] | Bidder A: Incl. track lighting. Bidder B: Track heads by tenant | 18400 | 2 | Bidder B | 18400 | 18400
06 820 | HVAC | Yes | Bidder A | 13100 | Bidder B | 13700 | [6 empty] | Bidder B: Incl. balancing report | 13100 | 1 | Bidder A | 13100 | 13100
06 810 | Sprinkler relocation | Yes | Bidder A | 5480 | Bidder B | 5760 | Bidder C | [5 empty] | Bidder A: Landlord's sprinkler contractor. Bidder C: Declined | 5480 | 1 | Bidder A | 5480 | 5480
06 830 | Fire alarm devices, allowance | Yes | [9 empty] | 3000 |  |  |  | Allowance | 3000 | 3000
[16 empty] | Total in the bid |  | 39980
Note on C6: Type a name to start a package, for example Firestopping.
Note on D6: Leave blank or Yes to count the package. No leaves it out of the bid but keeps its figures.
Note on M6: Leave blank to carry the lowest quote. Type 1, 2, 3 or 4 to carry that quote instead.
Note on N6: Carried only when there are no quotes yet.
Note on P6: The lowest quote above zero.
Note on Q6: Which quote is carried (1 to 4). The lowest unless you picked another.
Note on S6: The carried quote, or the allowance when there are no quotes.
Note on T6: What goes into the bid: the amount, or 0 if the package is switched off.

## General conditions
Free estimating spreadsheet from Bidfident
General conditions
Running costs that are not tied to one line of work: supervision, site office, small tools, bins. Weekly and monthly items can follow the job length from the Rates tab, so they grow if the job runs longer.
You type | [5 empty] | Worked out for you
Cost code | Description | Unit | Follows job length? | Quantity | Rate | Quantity used | Amount
01 100 | Supervision, lead carpenter | wk | Yes |  | 880 | 5 | 4400
01 160 | Storefront barricade, rented | wk | Yes |  | 145 | 5 | 725
01 190 | Building permit, tenant improvement | LS |  | 1 | 1900 | 1 | 1900
01 240 | Dumpster swaps | ea |  | 3 | 475 | 3 | 1425
01 260 | Final clean | LS |  | 1 | 760 | 1 | 760
[5 empty] | Total |  | 9210
Note on D6: wk = per week, mo = per month, day, hr, LS = lump sum, ea = each.
Note on E6: Yes makes a weekly (wk) or monthly (mo) item follow the job length on the Rates tab. Other units ignore it.
Note on F6: How many, when the item does not follow the job length.
Note on H6: The quantity that is used: the job length (in weeks, or in months = weeks divided by 52 over 12) for items that follow it, otherwise what you typed.
Note on I6: Quantity used x rate, rounded to the cent.

## Bid summary
Free estimating spreadsheet from Bidfident
Bid summary
Your bid, worked out in the order the calculations run. Each amount is rounded to the cent where it is worked out, so the column adds up exactly. Nothing on this tab is typed: change the other tabs and it follows.
Job | Retail store tenant improvement (example)
Location ¦ Bid due ¦ Length | Scottsdale, AZ ¦ 11/27/2026 ¦ 5 weeks
Item | Amount | How it is worked out
Own work | 95841.58 | The lines on the Estimate tab, apart from any marked Excluded.
Labor | 43793.6
Materials | 50709.98
Equipment | 1338
Subcontractors | 39980 | The quote carried for each package, or its allowance.
General conditions | 9210 | From the General conditions tab.
Direct cost | 145031.58 | Own work + subcontractors + general conditions
Contingency | 7251.58 | 5% of direct cost
Fee | 18273.98 | 12% of direct cost plus contingency
Subtotal before the bond | 170557.14 | Direct cost + contingency + fee.
Bond | 1705.57 | 1% of the subtotal
Insurance | 852.79 | 0.5% of the subtotal
Bid total | 173115.5 | The price you submit.
Sales tax, for reference | 0 | 0%, shown separately and not part of the bid total. Set your rate on the Rates tab.
Bid total including sales tax | 173115.5 | For reference.
Left out of the bid (Excluded lines) | 9960 | Priced so you can see them, added to nothing.
Lines that need a look | 0 | Every line has what it needs.
When your spreadsheet gets heavy
Bidfident does these same sums on a page, and adds what a spreadsheet cannot do:
Every bid in one place, with saved versions you can compare with now and restore.
Totals by cost code and by area, worked out for you.
It can read the Estimate tab of this spreadsheet, so your lines come across.
See it on an example job:
See Bidfident | bidfident.com/us

## Quote
Quote
Date | 2026-11-27
Valid for (days) | 30
Valid until | 2026-12-27
Reference | Q-0001
From
Your business | Sample Tenant Improvements Co.
Contact | Name, phone and email
Address | Street, town, postcode
To
Customer | Sample Customer
Address | Street, town, postcode
Job
Job | Retail store tenant improvement (example)
Location | Scottsdale, AZ
Expected length | 5 weeks
Scope of work
The tenant improvements work listed in our estimate, including materials, labor and equipment. Work areas left clean and tidy at the end of each day.
Not included
Anything not listed above. Work by other trades, permits and fees, unless stated above.
Price
Price |  | 173115.5
Sales tax is not included
Terms
Payment: 30% on acceptance, the balance within 14 days of completion. This price holds until the date above. Changes to the scope are priced before the work starts.
Acceptance
Signed for the customer
| Name and signature | Date
Signed for Sample Tenant Improvements Co.
| Name and signature | Date
Prepared with a free estimating spreadsheet from Bidfident, bidfident.com
Note on C3: This page goes to your customer, so its boxes are white, not yellow. Type in the boxes down the page; the job and the price come from the other tabs. Print it or save it as a PDF.
Note on C18: From the Rates tab.
Note on C19: From the Rates tab.
Note on C20: From the Rates tab.
Note on D31: The price is worked out on the Bid summary tab and cannot be typed over here.

## Codes
Free estimating spreadsheet from Bidfident
Starter cost codes
Bidfident's own starter list for tenant improvements, with the 01 codes for site set-up and running costs: one code for each kind of work you price. Pick one in the Cost code column on the Estimate tab, or type your own. Every code starts with a two-digit number, which is how Bidfident groups an estimate. Change the list to suit your business: rename, delete, or add codes between the numbers.
Codes
Code | Description | Unit
01 100 | Project management and supervision | wk
01 110 | Mobilization and demobilization | ls
01 120 | Site office and storage | wk
01 130 | Temporary power and lighting | wk
01 140 | Temporary heat and ventilation | wk
01 150 | Washrooms and handwashing | wk
01 160 | Fencing and signs | ls
01 170 | Safety plan and training | ls
01 180 | Safety gear and first aid | ls
01 190 | Permits and fees | ls
01 200 | Insurance and bonds | ls
01 210 | Layout and surveying | day
01 220 | Scaffold and access equipment | wk
01 230 | Hoisting and deliveries | day
01 240 | Dumpsters and waste removal | ea
01 250 | Daily cleaning | wk
01 260 | Final cleaning | ls
01 270 | Protection of existing floors and finishes | ls
01 280 | Site vehicles and fuel | ls
01 290 | Small tools and supplies | ls
01 300 | Drawings and submittals | ls
01 310 | Testing and inspections | ls
01 320 | Handover documents and manuals | ls
01 330 | Warranty and call backs | ls
01 340 | Allowances | ls
01 350 | Overtime and premium time | hr
01 360 | Weather protection | ls
01 370 | Meetings and site paperwork | hr
06 700 | Strip out of existing space | SF
06 710 | New partition walls | LF
06 720 | Suspended ceilings | SF
06 730 | Doors and hardware | ea
06 740 | Glass partitions and storefront | LF
06 750 | Floor finishes | SF
06 760 | Wall finishes and paint | SF
06 770 | Millwork and counters | LF
06 780 | Base and trim | LF
06 790 | Lighting changes | ea
06 800 | Power and data outlets | ea
06 810 | Sprinkler heads moved or added | ea
06 820 | Air outlets moved or added | ea
06 830 | Fire alarm devices moved or added | ea
06 840 | Signage and graphics | ea
06 850 | Washroom upgrades | ea
06 860 | Landlord approvals and drawings | ls
06 870 | After hours access costs | ls
06 880 | Extra work by the hour | hr
Free to use for your own bids. Change it to suit your business. Please don't resell it or hand it out as your own list.
Bidfident's own starter list, version 1, October 2026. Not affiliated with or endorsed by CSI, CSC or RICS.